## Sheet1
issue_id | issue_title | issue_type | control_deficiency | root_cause | symptoms | risk_description | success_criteria | issue_status | issue_rag_status | issue_rag_justification | original_mitigation_date | current_mitigation_date | mitigation_date_change_count | open_action_plans | total_action_plans | severity_rating | created_on | last_modified_on | group_id | group_name | division_id | division_name | unit_id | unit_name | area_id | area_name | sector_id | sector_name | segment_id | segment_name | function_id | function_name | l0_location_id | l0_location_name | region_id | region_name | sub_region_id | sub_region_name | country_id | country_name | company_id | company_short_name | issue_owner | issue_owner_gpn | issue_administrator | issue_administrator_gpn | issue_delegate | issue_delegate_gpn | first_level_reviewer | first_level_reviewer_gpn | orc_reviewer | orc_reviewer_gpn | orc_articulation_check | orc_rating_check | orc_mitigation_date_check | orc_action_plan_check | orc_mapping_check | regulatory_manager | regulatory_manager_gpn | regulator_country | regulator_type | audit_rating | audit_report_id | finding_id | mra_mria | dsori_program | gsori_program | eandy_relevant | operating_committee | reprioritization_risk_acceptance_justification | risk_acceptance_approval_date | category_flags | draft_date | open_grace_period_date | open_date | completed_date | closed_date | last_comment | last_comment_date | last_commenter | last_commenter_gpn | related_function_ids | related_function_names | related_location_ids | related_location_names | linked_control_ids | related_issue_ids | risk_themes
ISSUE-3746317213 | Internal Audit Observation - Monitoring Control Gap - Group Functions | Audit | Internal audit identified that Client Suitability controls are not operating effectively. Testing revealed gaps in execution and documentation. | Insufficient training and awareness among staff | Documentation gaps and missing evidence | Financial losses from operational errors | All Client Suitability controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-01-11 | 2024-05-02 | 1 | 4 | 5 | 5 | 2023-03-07 | 2025-04-21 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Isabella Weber | 79182797 | Margaret Wang | 22534217 | Evelyn Fischer |  | Alexander Martinez | 13278320 | [11 empty] | Satisfactory | AR-2024003 | F-586 |  | TRUE | FALSE | FALSE | Audit Committee |  |  | BCBS239 Control, CCAR Control | 2023-03-07 |  | 2023-05-17 |  |  | Status update as of 2025-04-21. Remediation activities progressing. | 2025-04-21 | James Miller | 67062156 | N14963 | Deal Execution | 4300, 2100, 3200 | UBS Securities Japan Co Ltd, UBS AG London Branch, UBS Financial Services Inc | CTRL-6756332150, CTRL-4095476665 |  | Client Suitability, Physical Security
ISSUE-9697354961 | Internal Audit Observation - Monitoring Control Gap - Investment Bank | Audit | Internal audit identified that Legal Risk controls are not operating effectively. Testing revealed gaps in execution and documentation. | Organizational changes affecting ownership | Control exceptions not properly escalated | Client complaints and relationship impact | All Legal Risk controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2024-12-20 | 2025-05-20 | 1 | 3 | 3 | 4 | 2024-07-02 | 2025-04-05 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Sarah Young | 20399639 | David Jackson | 46468984 |  | 20814950 | Lucas Martinez | 41039390 | Thomas Martinez | 38716269 | Pass | Fail | Fail | Fail | N/A |  |  |  |  | Needs Improvement | AR-2024704 | F-163 |  | TRUE | FALSE | FALSE | Risk Committee | Business priority assessment completed. |  | Application Control, Key Control | 2024-07-02 |  | 2024-09-30 |  |  | Status update as of 2025-04-05. Remediation activities progressing. | 2025-04-05 | John Fischer | 62343121 | N40313, N40413 | Transaction Monitoring, Capital Calculations | 3100, 4300, 2210 | UBS Securities LLC, UBS Securities Japan Co Ltd, UBS Europe SE Frankfurt | CTRL-9573276057, CTRL-2948728483, CTRL-1958682846 |  | Legal Risk, Talent and Resource Management
ISSUE-1958682846 | Internal Audit Observation - Monitoring Control Gap - Investment Bank | Audit | Internal audit identified that Operational Resilience controls are not operating effectively. Testing revealed gaps in execution and documentation. | Insufficient training and awareness among staff | Documentation gaps and missing evidence | Increased scrutiny from regulators | All Operational Resilience controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2025-03-02 | 2025-03-02 | 0 | 1 | 4 | 4 | 2024-05-27 | 2025-10-25 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3200 | UBS Financial Services Inc | Barbara Martinez | 68450095 | Amelia Schmidt | 92666356 | Kevin Wright |  | Nancy Schmidt | 53258988 | Evelyn Garcia | 47437115 | Fail | Pass | Fail | N/A | N/A |  |  |  |  | Unsatisfactory | AR-2024553 | F-444 |  | TRUE | FALSE | FALSE | Audit Committee |  |  | Financial Reporting Control, Regulatory Control | 2024-05-27 |  | 2024-08-21 |  |  | Status update as of 2025-10-25. Remediation activities progressing. | 2025-10-25 | Edward Schmidt | 84597009 | N40313 | Transaction Monitoring | 2210 | UBS Europe SE Frankfurt | CTRL-3030106617, CTRL-1470939445 |  | Operational Resilience
ISSUE-9703905715 | Internal Audit Finding - Reconciliation Control Failure - Group Functions | Audit | Internal audit identified that Data Management controls are not operating effectively. Testing revealed gaps in execution and documentation. | Lack of automated controls and manual workarounds | Control exceptions not properly escalated | Financial losses from operational errors | All Data Management controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2024-12-22 | 2024-12-22 | 0 | 1 | 4 | 3 | 2024-05-18 | 2024-11-05 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3200 | UBS Financial Services Inc | John Weber | 49625201 | Emma Harris | 46840133 |  | 16582607 | Edward Lopez | 48412328 | Daniel Li | 39394291 | N/A | Pass | N/A | Fail | N/A |  |  |  |  | Unsatisfactory | AR-2025701 | F-797 |  | TRUE | TRUE | TRUE | Operating Committee |  |  | CCAR Control, SOX Control | 2024-05-18 |  | 2024-08-14 |  |  | Status update as of 2024-11-05. Remediation activities progressing. | 2024-11-05 | David Chen | 65767881 | N20113 | Investment Advisory | 4100 | UBS AG Hong Kong Branch | CTRL-7887950851, CTRL-6488854841, CTRL-2867302554 | ISSUE-9963334018, ISSUE-9697354961 | Data Management
ISSUE-7825844140 | Internal Audit Finding - Reconciliation Control Failure - Group Functions | Audit | Internal audit identified that Process Execution controls are not operating effectively. Testing revealed gaps in execution and documentation. | Organizational changes affecting ownership | Inconsistent application of procedures | Potential regulatory sanctions or fines | All Process Execution controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2023-02-24 | 2023-02-24 | 0 | 5 | 5 | 5 | 2022-06-15 | 2024-03-08 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Edward Weber | 70896652 | Joshua Thompson | 23311507 | Mia Thomas |  | Daniel Martin | 55490631 | Barbara Harris | 65833185 | N/A | Pass | Fail | Fail | Fail |  |  |  |  | Unsatisfactory | AR-2024045 | F-483 |  | TRUE | FALSE | TRUE | Risk Committee | Business priority assessment completed. |  | Financial Reporting Control | 2022-06-15 |  | 2022-09-04 |  |  | Status update as of 2024-03-08. Remediation activities progressing. | 2024-03-08 | Lucas Brown | 88714010 | N40313, N30113, N10122 | Transaction Monitoring, Portfolio Management, Options Trading | 4100, 4200 | UBS AG Hong Kong Branch, UBS AG Singapore Branch | CTRL-3030106617, CTRL-2812140441, CTRL-4131575764, CTRL-3361388464 |  | Process Execution, Technology Change Management
ISSUE-2445662585 | Internal Audit Observation - Monitoring Control Gap - Investment Bank | Audit | Internal audit identified that Transaction Processing controls are not operating effectively. Testing revealed gaps in execution and documentation. | Legacy systems limitations | Delayed or incomplete reporting | Client complaints and relationship impact | All Transaction Processing controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2023-01-25 | 2023-01-25 | 0 | 0 | 5 | 4 | 2022-03-31 | 2024-08-31 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Matthew Moore | 81673763 | Evelyn Fischer | 72950208 | Alexander Kumar | 86560394 | Matthew King | 47818761 | Thomas Martin | 31751079 | Pass | N/A | Pass | Fail | Pass |  |  |  |  | Unsatisfactory | AR-2024969 | F-995 |  | FALSE | TRUE | TRUE | Operating Committee |  |  | Manual Control, CCAR Control | 2022-03-31 |  | 2022-06-22 | 2025-03-23 | 2024-04-03 | Status update as of 2024-08-31. Remediation activities progressing. | 2024-08-31 | Daniel Young | 56920514 | N40113 | Control Testing | 4200 | UBS AG Singapore Branch | CTRL-9786748825, CTRL-7010379415, CTRL-7635473142 |  | Transaction Processing
ISSUE-8429141456 | Internal Audit Finding - Control Design Deficiency - Asset Management | Audit | Internal audit identified that Financial Crime Prevention controls are not operating effectively. Testing revealed gaps in execution and documentation. | Lack of automated controls and manual workarounds | Inconsistent application of procedures | Reputational damage to the firm | All Financial Crime Prevention controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2023-03-04 | 2023-03-04 | 0 | 0 | 4 | 3 | 2022-10-16 | 2025-01-28 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Henry Chen | 87535841 | Robert Taylor | 31386576 |  | 76942394 | Jennifer Lopez | 13110670 | Isabella Harris | 77839607 | Fail | Pass | Pass | N/A | Fail |  |  |  |  | Satisfactory | AR-2023208 | F-388 |  | FALSE | FALSE | FALSE | Risk Committee | Business priority assessment completed. |  | Financial Reporting Control, IT General Control | 2022-10-16 |  | 2022-12-08 | 2024-02-16 | 2025-02-14 | Status update as of 2025-01-28. Remediation activities progressing. | 2025-01-28 | Sophia Taylor | 58657117 | N20213, N10122, N40113 | Trust Services, Options Trading, Control Testing | 4300, 4200, 3200 | UBS Securities Japan Co Ltd, UBS AG Singapore Branch, UBS Financial Services Inc | CTRL-7517938612, CTRL-4888749350, CTRL-8086172302 |  | Financial Crime Prevention, Legal Risk
ISSUE-6884882440 | Internal Audit Finding - Reconciliation Control Failure - Investment Bank | Audit | Internal audit identified that Process Execution controls are not operating effectively. Testing revealed gaps in execution and documentation. | Inadequate process documentation and procedures | Delayed or incomplete reporting | Financial losses from operational errors | All Process Execution controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2024-04-23 | 2024-04-23 | 0 | 2 | 3 | 3 | 2023-09-09 | 2024-03-05 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Evelyn Lopez | 89699345 | Margaret Taylor | 71453148 |  |  | Patricia Wang | 93240786 | Thomas Wang | 69085720 | Fail | Fail | N/A | N/A | Pass |  |  |  |  | Needs Improvement | AR-2024314 | F-717 |  | TRUE | FALSE | FALSE | Audit Committee | Business priority assessment completed. | 2024-10-25 | Application Control, BCBS239 Control, Financial Reporting Control | 2023-09-09 |  | 2023-11-02 |  |  | Status update as of 2024-03-05. Remediation activities progressing. | 2024-03-05 | Sarah Harris | 58991556 | N40413 | Capital Calculations | 1000 | UBS AG Zurich | CTRL-8664882079 |  | Process Execution
ISSUE-6649827836 | Audit Observation - Process Documentation Gaps - Investment Bank | Audit | Internal audit identified that Transaction Processing controls are not operating effectively. Testing revealed gaps in execution and documentation. | Organizational changes affecting ownership | Increased error rates in processing | Reputational damage to the firm | All Transaction Processing controls operating effectively with documented evidence and no exceptions. | Open | Red | Issue Mitigation Date at significant risk. Key dependencies delayed and remediation plan requires revision. | 2025-07-07 | 2025-07-07 | 0 | 3 | 3 | 3 | 2024-10-13 | 2024-09-22 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Emma Wang | 67622968 | Sarah Jones | 45292504 | Brian Jones |  | Joshua Kumar | 17440911 | Susan Wilson | 59350218 | Pass | Fail | Pass | N/A | N/A |  |  |  |  | Unsatisfactory | AR-2023473 | F-333 |  | TRUE | TRUE | TRUE | Audit Committee |  |  | CCAR Control | 2024-10-13 |  | 2025-01-10 |  |  | Status update as of 2024-09-22. Remediation activities progressing. | 2024-09-22 | Oliver Martin | 40133935 | N20113, N40113 | Investment Advisory, Control Testing | 4100, 1000, 2100 | UBS AG Hong Kong Branch, UBS AG Zurich, UBS AG London Branch | CTRL-6756332150, CTRL-3615507143, CTRL-1983297492 | ISSUE-8293453178 | Transaction Processing
ISSUE-2149938334 | Internal Audit Finding - Control Design Deficiency - Group Functions | Audit | Internal audit identified that Sanctions Compliance controls are not operating effectively. Testing revealed gaps in execution and documentation. | Legacy systems limitations | Inconsistent application of procedures | Potential regulatory sanctions or fines | All Sanctions Compliance controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-08-05 | 2024-08-05 | 0 | 1 | 2 | 4 | 2024-01-26 | 2024-11-07 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Susan Taylor | 83357939 | Evelyn Martinez | 10856024 | Emma Moore | 95354668 | James Wang | 10196231 | Thomas Fischer | 23951801 | Pass | N/A | Pass | Fail | Fail |  |  |  |  | Satisfactory | AR-2023584 | F-828 |  | FALSE | TRUE | TRUE | Audit Committee | Business priority assessment completed. |  | Financial Reporting Control, Application Control, SOX Control | 2024-01-26 |  | 2024-04-02 | 2024-04-07 |  | Status update as of 2024-11-07. Remediation activities progressing. | 2024-11-07 | Joshua Rodriguez | 95525640 | N10122, N10112 | Options Trading, Electronic Trading | 1000, 2210 | UBS AG Zurich, UBS Europe SE Frankfurt | CTRL-2566942273, CTRL-8235363119, CTRL-5284391408 | ISSUE-8934927891, ISSUE-3479708607 | Sanctions Compliance, Conduct Risk
ISSUE-2351531223 | Internal Audit Finding - Control Design Deficiency - Investment Bank | Audit | Internal audit identified that Operational Resilience controls are not operating effectively. Testing revealed gaps in execution and documentation. | Inadequate process documentation and procedures | Increased error rates in processing | Reputational damage to the firm | All Operational Resilience controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2025-06-02 | 2025-06-02 | 0 | 2 | 2 | 4 | 2024-07-09 | 2024-05-03 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Mia Garcia | 31154777 | Jennifer Williams | 38859601 | Robert Martinez |  | Evelyn Li | 63183031 | Joshua Brown | 50109721 | Fail | Pass | Pass | Fail | Fail |  |  |  |  | Unsatisfactory | AR-2025254 | F-355 |  | TRUE | FALSE | TRUE | Audit Committee |  |  | CCAR Control | 2024-07-09 |  | 2024-08-20 |  |  | Status update as of 2024-05-03. Remediation activities progressing. | 2024-05-03 | Patricia Kumar | 94597104 | N10122, N20213, N40413 | Options Trading, Trust Services, Capital Calculations | 2210 | UBS Europe SE Frankfurt | CTRL-2452066459, CTRL-7567496105 | ISSUE-7887950851 | Operational Resilience
ISSUE-2970753705 | Audit Issue - Access Management Deficiency - Asset Management | Audit | Internal audit identified that Financial Crime Prevention controls are not operating effectively. Testing revealed gaps in execution and documentation. | Lack of automated controls and manual workarounds | Documentation gaps and missing evidence | Increased scrutiny from regulators | All Financial Crime Prevention controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2022-11-24 | 2023-05-17 | 1 | 3 | 4 | 3 | 2022-02-27 | 2024-05-25 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Isabella Brown | 41222178 | Edward Moore | 12674689 | James Wang | 37040091 | Lucas Wang | 33818260 | Robert Brown | 12941099 | Pass | N/A | N/A | Pass | Pass |  |  |  |  | Unsatisfactory | AR-2024495 | F-174 |  | FALSE | FALSE | TRUE | Operating Committee |  |  | IT General Control | 2022-02-27 |  | 2022-05-18 |  |  | Status update as of 2024-05-25. Remediation activities progressing. | 2024-05-25 | Susan Chen | 33381086 | N40313, N30113, N20113 | Transaction Monitoring, Portfolio Management, Investment Advisory | 1000, 3100, 4300 | UBS AG Zurich, UBS Securities LLC, UBS Securities Japan Co Ltd | CTRL-1667779376, CTRL-4466589567, CTRL-8664882079 |  | Financial Crime Prevention
ISSUE-7010379415 | Audit Issue - Access Management Deficiency - Group Functions | Audit | Internal audit identified that Business Continuity controls are not operating effectively. Testing revealed gaps in execution and documentation. | Organizational changes affecting ownership | Inconsistent application of procedures | Increased scrutiny from regulators | All Business Continuity controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2024-03-26 | 2024-03-26 | 0 | 0 | 1 | 5 | 2023-04-28 | 2025-02-08 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SB | UK & Ireland | C782 | United Kingdom | 2100 | UBS AG London Branch | Jessica Martinez | 26143959 | Matthew Anderson | 32436477 | Alexander Rodriguez |  | Isabella Thompson | 37101146 | Charlotte Mueller | 52916049 | N/A | Pass | Pass | Fail | N/A |  |  |  |  | Needs Improvement | AR-2025262 | F-433 |  | FALSE | FALSE | TRUE | Executive Committee |  |  | Automated Control, SOX Control, Manual Control | 2023-04-28 |  | 2023-07-03 | 2024-04-13 | 2024-10-19 | Status update as of 2025-02-08. Remediation activities progressing. | 2025-02-08 | Kevin Li | 65148727 | N40113, N40213 | Control Testing, DevOps | 4300, 2100, 2210 | UBS Securities Japan Co Ltd, UBS AG London Branch, UBS Europe SE Frankfurt | CTRL-7483366056, CTRL-5693307665, CTRL-7517938612 |  | Business Continuity, Regulatory Compliance
ISSUE-7483366056 | Audit Finding - Data Quality Control Weakness - Asset Management | Audit | Internal audit identified that Anti-Money Laundering controls are not operating effectively. Testing revealed gaps in execution and documentation. | Organizational changes affecting ownership | Increased error rates in processing | Financial losses from operational errors | All Anti-Money Laundering controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2022-12-10 | 2022-12-10 | 0 | 0 | 2 | 5 | 2022-02-26 | 2025-08-08 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Harper Schmidt | 97454571 | Christopher Johnson | 11194267 |  |  | Amelia Smith | 40033905 | [11 empty] | Needs Improvement | AR-2025492 | F-924 |  | FALSE | FALSE | FALSE | Executive Committee | Business priority assessment completed. |  | Application Control | 2022-02-26 |  | 2022-04-16 | 2025-11-24 |  | Status update as of 2025-08-08. Remediation activities progressing. | 2025-08-08 | Jessica Harris | 88448538 | N10112 | Electronic Trading | 4100, 3200, 4300 | UBS AG Hong Kong Branch, UBS Financial Services Inc, UBS Securities Japan Co Ltd | CTRL-6924716023, CTRL-4888749350, CTRL-4460967357 |  | Anti-Money Laundering
ISSUE-3694860228 | Audit Observation - Process Documentation Gaps - Global Wealth Management | Audit | Internal audit identified that Third Party Management controls are not operating effectively. Testing revealed gaps in execution and documentation. | Inadequate process documentation and procedures | Documentation gaps and missing evidence | Client complaints and relationship impact | All Third Party Management controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2025-01-05 | 2025-01-05 | 0 | 1 | 4 | 5 | 2024-07-26 | 2024-07-03 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20200 | High Net Worth | N20210 | Wealth Planning | N20211 | Tax Advisory | N20212 | Estate Planning | N20213 | Trust Services | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Robert Brown | 10632635 | Matthew Schmidt | 38102825 | Henry Wilson |  | Isabella Rodriguez | 92474074 | Linda Thompson | 64142556 | Fail | Fail | Fail | Pass | Pass |  |  |  |  | Unsatisfactory | AR-2023817 | F-848 |  | FALSE | TRUE | FALSE | Audit Committee |  |  | BCBS239 Control, Automated Control, Financial Reporting Control | 2024-07-26 |  | 2024-09-13 | 2024-05-12 |  | Status update as of 2024-07-03. Remediation activities progressing. | 2024-07-03 | Benjamin White | 77556678 | N20213, N14963, N10122 | Trust Services, Deal Execution, Options Trading | 3200 | UBS Financial Services Inc | CTRL-4095476665, CTRL-8664882079, CTRL-4274958945 |  | Third Party Management
ISSUE-9573276057 | Audit Finding - Data Quality Control Weakness - Investment Bank | Audit | Internal audit identified that Operational Resilience controls are not operating effectively. Testing revealed gaps in execution and documentation. | Resource constraints and competing priorities | Delayed or incomplete reporting | Potential regulatory sanctions or fines | All Operational Resilience controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2025-03-21 | 2025-05-15 | 1 | 1 | 4 | 4 | 2024-11-13 | 2024-09-19 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10110 | Cash Equities | N10111 | Execution Services | N10112 | Electronic Trading | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Benjamin Anderson | 15294153 | David Kumar | 51970837 |  |  | Oliver Smith | 28574987 | Henry Wang | 57986515 | Fail | N/A | Fail | N/A | Pass |  |  |  |  | Needs Improvement | AR-2024404 | F-287 |  | TRUE | FALSE | FALSE | Executive Committee |  |  | IT General Control, CCAR Control | 2024-11-13 |  | 2024-12-20 | 2024-05-15 |  | Status update as of 2024-09-19. Remediation activities progressing. | 2024-09-19 | Sophia Wilson | 23920137 | N40413, N40213 | Capital Calculations, DevOps | 4300, 2210, 3200 | UBS Securities Japan Co Ltd, UBS Europe SE Frankfurt, UBS Financial Services Inc | CTRL-1422701550, CTRL-8110054933, CTRL-8086172302, CTRL-1958682846 | ISSUE-9786748825 | Operational Resilience
ISSUE-8047877267 | Internal Audit Observation - Monitoring Control Gap - Group Functions | Audit | Internal audit identified that Business Continuity controls are not operating effectively. Testing revealed gaps in execution and documentation. | Organizational changes affecting ownership | Documentation gaps and missing evidence | Potential regulatory sanctions or fines | All Business Continuity controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-12-05 | 2024-12-05 | 0 | 1 | 1 | 3 | 2024-02-21 | 2025-12-02 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Matthew Moore | 95065651 | Maria Taylor | 35970823 |  |  | William Anderson | 33326387 | Joshua Davis | 60626689 | Pass | Fail | Fail | N/A | Fail |  |  |  |  | Satisfactory | AR-2023660 | F-698 |  | FALSE | TRUE | FALSE | Executive Committee |  |  | Financial Reporting Control | 2024-02-21 |  | 2024-04-29 |  |  | Status update as of 2025-12-02. Remediation activities progressing. | 2025-12-02 | Sophia Fischer | 75840632 | N40313, N30113, N10122 | Transaction Monitoring, Portfolio Management, Options Trading | 4100, 3200, 2210 | UBS AG Hong Kong Branch, UBS Financial Services Inc, UBS Europe SE Frankfurt | CTRL-4274958945, CTRL-1939042955 | ISSUE-7665963761 | Business Continuity
ISSUE-2948728483 | Audit Finding - Data Quality Control Weakness - Global Wealth Management | Audit | Internal audit identified that Outsourcing Risk controls are not operating effectively. Testing revealed gaps in execution and documentation. | Legacy systems limitations | Increased error rates in processing | Increased scrutiny from regulators | All Outsourcing Risk controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2024-12-07 | 2024-12-07 | 0 | 4 | 5 | 4 | 2024-08-02 | 2024-03-09 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20200 | High Net Worth | N20210 | Wealth Planning | N20211 | Tax Advisory | N20212 | Estate Planning | N20213 | Trust Services | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Evelyn Miller | 48270459 | Margaret Jones | 35970938 |  |  | Margaret Fischer | 88405961 | Charlotte Kumar | 52457517 | Fail | Pass | Pass | Fail | Pass |  |  |  |  | Satisfactory | AR-2025918 | F-857 |  | FALSE | FALSE | FALSE | Audit Committee |  |  | Application Control, Automated Control | 2024-08-02 |  | 2024-09-23 |  |  | Status update as of 2024-03-09. Remediation activities progressing. | 2024-03-09 | Jennifer Lopez | 84044139 | N14963 | Deal Execution | 2210, 4200, 1000 | UBS Europe SE Frankfurt, UBS AG Singapore Branch, UBS AG Zurich | CTRL-6687206971, CTRL-2625792787 |  | Outsourcing Risk
ISSUE-3615507143 | Internal Audit Observation - Monitoring Control Gap - Group Functions | Audit | Internal audit identified that Operational Resilience controls are not operating effectively. Testing revealed gaps in execution and documentation. | Insufficient training and awareness among staff | Control exceptions not properly escalated | Financial losses from operational errors | All Operational Resilience controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-09-01 | 2024-09-01 | 0 | 1 | 3 | 4 | 2024-02-10 | 2024-12-27 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | James Rodriguez | 69042204 | Henry Moore | 20346606 | Sarah Thomas |  | Henry Kumar | 90801793 | Mia Moore | 65648506 | Fail | N/A | Pass | Fail | N/A |  |  |  |  | Needs Improvement | AR-2024963 | F-315 |  | TRUE | FALSE | TRUE | Audit Committee |  |  | CCAR Control | 2024-02-10 |  | 2024-04-20 | 2025-06-08 |  | Status update as of 2024-12-27. Remediation activities progressing. | 2024-12-27 | Oliver Martinez | 17504382 | N20213 | Trust Services | 4200 | UBS AG Singapore Branch | CTRL-3030106617 | ISSUE-7635473142, ISSUE-8995970241 | Operational Resilience, Organizational Culture
ISSUE-5951406973 | Audit Issue - Access Management Deficiency - Group Functions | Audit | Internal audit identified that Regulatory Compliance controls are not operating effectively. Testing revealed gaps in execution and documentation. | Inadequate process documentation and procedures | Control exceptions not properly escalated | Reputational damage to the firm | All Regulatory Compliance controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2025-06-25 | 2025-06-25 | 0 | 1 | 5 | 3 | 2024-11-12 | 2025-12-03 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Lucas Miller | 12222998 | Alexander Martin | 30073763 | Amelia Wright | 90505645 | Oliver Davis | 22507745 | Andrew Rodriguez | 90996996 | N/A | Pass | N/A | N/A | Fail |  |  |  |  | Unsatisfactory | AR-2024724 | F-479 |  | TRUE | FALSE | TRUE | Executive Committee |  |  | Automated Control, SOX Control, IT General Control | 2024-11-12 |  | 2024-12-20 |  |  | Status update as of 2025-12-03. Remediation activities progressing. | 2025-12-03 | Michael Wright | 41207351 | N20213 | Trust Services | 4200, 1000, 2210 | UBS AG Singapore Branch, UBS AG Zurich, UBS Europe SE Frankfurt | CTRL-6317189421 | ISSUE-6756332150 | Regulatory Compliance
ISSUE-9285415473 | Internal Audit Observation - Monitoring Control Gap - Investment Bank | Audit | Internal audit identified that Regulatory Change controls are not operating effectively. Testing revealed gaps in execution and documentation. | Organizational changes affecting ownership | Control exceptions not properly escalated | Increased scrutiny from regulators | All Regulatory Change controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2024-09-12 | 2024-09-12 | 0 | 0 | 1 | 4 | 2023-10-09 | 2025-07-29 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10110 | Cash Equities | N10111 | Execution Services | N10112 | Electronic Trading | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Henry Brown | 38919534 | Michael Wright | 94538675 |  | 44865621 | Maria Kumar | 85208908 | [11 empty] | Unsatisfactory | AR-2024056 | F-452 |  | TRUE | FALSE | TRUE | Operating Committee | Business priority assessment completed. | 2024-07-22 | Automated Control, Manual Control, CCAR Control | 2023-10-09 |  | 2023-12-27 | 2024-10-18 | 2024-12-29 | Status update as of 2025-07-29. Remediation activities progressing. | 2025-07-29 | Robert Lopez | 69985944 | N40113 | Control Testing | 3200, 3100, 4100 | UBS Financial Services Inc, UBS Securities LLC, UBS AG Hong Kong Branch | CTRL-7887950851, CTRL-1965067727 | ISSUE-3694860228, ISSUE-7483366056 | Regulatory Change, Third Party Management
ISSUE-1248786714 | Audit Finding - Data Quality Control Weakness - Group Functions | Audit | Internal audit identified that Business Continuity controls are not operating effectively. Testing revealed gaps in execution and documentation. | Legacy systems limitations | Documentation gaps and missing evidence | Financial losses from operational errors | All Business Continuity controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2025-04-07 | 2025-08-28 | 1 | 1 | 3 | 3 | 2024-09-13 | 2024-11-11 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40400 | Group Finance | N40410 | Financial Reporting | N40411 | Regulatory Reporting | N40412 | Capital Reporting | N40413 | Capital Calculations | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Lucas Li | 48488577 | Andrew Smith | 76025948 | Andrew Fischer |  | Linda Weber | 90128487 | Daniel Smith | 83579795 | Fail | Pass | Fail | N/A | Fail |  |  |  |  | Needs Improvement | AR-2024024 | F-267 |  | FALSE | FALSE | TRUE | Operating Committee |  |  | Automated Control, Regulatory Control, Manual Control | 2024-09-13 |  | 2024-11-23 |  |  | Status update as of 2024-11-11. Remediation activities progressing. | 2024-11-11 | Kevin Schmidt | 65419020 | N10122 | Options Trading | 1000 | UBS AG Zurich | CTRL-8293453178, CTRL-1965067727, CTRL-4095476665 |  | Business Continuity, Organizational Culture
ISSUE-5067116918 | Internal Audit Finding - Control Design Deficiency - Global Wealth Management | Audit | Internal audit identified that Conduct Risk controls are not operating effectively. Testing revealed gaps in execution and documentation. | Inadequate process documentation and procedures | Increased error rates in processing | Increased scrutiny from regulators | All Conduct Risk controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2022-08-19 | 2022-11-29 | 1 | 1 | 1 | 3 | 2022-02-15 | 2024-10-02 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20200 | High Net Worth | N20210 | Wealth Planning | N20211 | Tax Advisory | N20212 | Estate Planning | N20213 | Trust Services | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Susan Thomas | 55890766 | Christopher Fischer | 76893545 | Barbara Williams |  | Charlotte Brown | 45769504 | [11 empty] | Needs Improvement | AR-2023293 | F-656 |  | FALSE | TRUE | TRUE | Operating Committee | Business priority assessment completed. |  | BCBS239 Control | 2022-02-15 |  | 2022-04-10 |  |  | Status update as of 2024-10-02. Remediation activities progressing. | 2024-10-02 | Matthew Jackson | 14497675 | N40213 | DevOps | 2210, 3200, 4100 | UBS Europe SE Frankfurt, UBS Financial Services Inc, UBS AG Hong Kong Branch | CTRL-5774080233, CTRL-7010379415 |  | Conduct Risk
ISSUE-3361388464 | Audit Observation - Process Documentation Gaps - Group Functions | Audit | Internal audit identified that Cyber and Information Security controls are not operating effectively. Testing revealed gaps in execution and documentation. | Legacy systems limitations | Increased error rates in processing | Potential regulatory sanctions or fines | All Cyber and Information Security controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-02-08 | 2024-03-29 | 1 | 1 | 1 | 5 | 2023-03-04 | 2025-04-24 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Christopher Kumar | 17824896 | Margaret Schmidt | 81003974 |  |  | Jennifer Jones | 38977615 | Jessica Miller | 23586205 | N/A | Pass | N/A | Fail | Pass |  |  |  |  | Satisfactory | AR-2025156 | F-772 |  | TRUE | TRUE | FALSE | Risk Committee |  |  | Application Control, IT General Control, SOX Control | 2023-03-04 |  | 2023-04-13 | 2024-07-03 |  | Status update as of 2025-04-24. Remediation activities progressing. | 2025-04-24 | Karen Harris | 77738718 | N14963, N40313 | Deal Execution, Transaction Monitoring | 4300, 1000, 4200 | UBS Securities Japan Co Ltd, UBS AG Zurich, UBS AG Singapore Branch | CTRL-2137651678, CTRL-1470939445, CTRL-7114223633 |  | Cyber and Information Security, Market Conduct
ISSUE-7517938612 | Audit Observation - Process Documentation Gaps - Investment Bank | Audit | Internal audit identified that Cyber and Information Security controls are not operating effectively. Testing revealed gaps in execution and documentation. | Legacy systems limitations | Delayed or incomplete reporting | Financial losses from operational errors | All Cyber and Information Security controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2022-10-21 | 2022-10-21 | 0 | 1 | 3 | 5 | 2022-01-29 | 2024-04-23 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Harper Mueller | 83658696 | Andrew Martinez | 99692417 |  | 99057266 | Jessica Williams | 44286770 | Henry Brown | 48119652 | Pass | N/A | N/A | Fail | Pass |  |  |  |  | Needs Improvement | AR-2025682 | F-108 |  | TRUE | FALSE | FALSE | Operating Committee | Business priority assessment completed. |  | IT General Control, BCBS239 Control, Automated Control | 2022-01-29 |  | 2022-04-01 |  |  | Status update as of 2024-04-23. Remediation activities progressing. | 2024-04-23 | Benjamin Chen | 75050252 | N40313, N10122, N14963 | Transaction Monitoring, Options Trading, Deal Execution | 4300 | UBS Securities Japan Co Ltd | CTRL-9963334018 |  | Cyber and Information Security
ISSUE-2452066459 | Audit Issue - Segregation of Duties Weakness - Investment Bank | Audit | Internal audit identified that Intragroup Dependencies controls are not operating effectively. Testing revealed gaps in execution and documentation. | Resource constraints and competing priorities | Inconsistent application of procedures | Financial losses from operational errors | All Intragroup Dependencies controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-06-30 | 2024-06-30 | 0 | 0 | 1 | 4 | 2023-08-09 | 2024-10-28 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10110 | Cash Equities | N10111 | Execution Services | N10112 | Electronic Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Matthew Garcia | 77197151 | Mia Anderson | 88577462 | Kevin Rodriguez |  | Robert Young | 13343647 | Amelia King | 89230801 | N/A | Pass | Fail | Pass | Fail |  |  |  |  | Needs Improvement | AR-2025834 | F-764 |  | TRUE | TRUE | TRUE | Risk Committee |  |  | Manual Control | 2023-08-09 |  | 2023-10-23 | 2025-01-28 |  | Status update as of 2024-10-28. Remediation activities progressing. | 2024-10-28 | Joshua Wilson | 60825385 | N40113, N10112, N14963 | Control Testing, Electronic Trading, Deal Execution | 1000, 2210 | UBS AG Zurich, UBS Europe SE Frankfurt | CTRL-4466589567, CTRL-4131356954 | ISSUE-3392080953, ISSUE-9639245200 | Intragroup Dependencies
ISSUE-9894847574 | Internal Audit Finding - Control Design Deficiency - Group Functions | Audit | Internal audit identified that Regulatory Change controls are not operating effectively. Testing revealed gaps in execution and documentation. | Organizational changes affecting ownership | Documentation gaps and missing evidence | Financial losses from operational errors | All Regulatory Change controls operating effectively with documented evidence and no exceptions. | Open | Red | Issue Mitigation Date at significant risk. Key dependencies delayed and remediation plan requires revision. | 2025-10-12 | 2025-10-12 | 0 | 5 | 5 | 3 | 2024-12-15 | 2025-12-13 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Edward Weber | 67318164 | Edward Chen | 44850980 | Margaret Li | 92448605 | Brian Lopez | 79753731 | Susan Lopez | 34146739 | N/A | Pass | N/A | Fail | Pass |  |  |  |  | Satisfactory | AR-2023485 | F-124 |  | FALSE | TRUE | TRUE | Executive Committee |  |  | BCBS239 Control, Key Control, Automated Control | 2024-12-15 |  | 2025-02-27 |  |  | Status update as of 2025-12-13. Remediation activities progressing. | 2025-12-13 | David Mueller | 19104802 | N20213, N40313 | Trust Services, Transaction Monitoring | 4100, 4200, 2100 | UBS AG Hong Kong Branch, UBS AG Singapore Branch, UBS AG London Branch | CTRL-4888749350 |  | Regulatory Change, Third Party Management
ISSUE-1983297492 | Internal Audit Observation - Monitoring Control Gap - Global Wealth Management | Audit | Internal audit identified that Business Continuity controls are not operating effectively. Testing revealed gaps in execution and documentation. | Lack of automated controls and manual workarounds | Delayed or incomplete reporting | Potential regulatory sanctions or fines | All Business Continuity controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2025-04-29 | 2025-04-29 | 0 | 1 | 5 | 3 | 2024-11-23 | 2024-02-07 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20100 | Ultra High Net Worth | N20110 | Private Banking | N20111 | Client Advisory | N20112 | Portfolio Management | N20113 | Investment Advisory | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Oliver Garcia | 54733393 | Barbara Williams | 23838227 | Jennifer Johnson | 51895110 | Harper Chen | 36918105 | Alexander Weber | 47131272 | N/A | Fail | Fail | N/A | Pass |  |  |  |  | Needs Improvement | AR-2023612 | F-261 |  | FALSE | TRUE | TRUE | Risk Committee |  |  | Regulatory Control, CCAR Control | 2024-11-23 |  | 2025-02-21 |  |  | Status update as of 2024-02-07. Remediation activities progressing. | 2024-02-07 | David Jackson | 32988138 | N20213 | Trust Services | 4100, 3200, 3100 | UBS AG Hong Kong Branch, UBS Financial Services Inc, UBS Securities LLC | CTRL-1667779376 |  | Business Continuity, Sanctions Compliance
ISSUE-4888749350 | Internal Audit Finding - Reconciliation Control Failure - Investment Bank | Audit | Internal audit identified that Cyber and Information Security controls are not operating effectively. Testing revealed gaps in execution and documentation. | Resource constraints and competing priorities | Delayed or incomplete reporting | Increased scrutiny from regulators | All Cyber and Information Security controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2025-03-31 | 2025-03-31 | 0 | 0 | 5 | 4 | 2024-07-02 | 2024-07-21 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10110 | Cash Equities | N10111 | Execution Services | N10112 | Electronic Trading | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Isabella King | 23054418 | Barbara Fischer | 96492401 | Barbara Wright |  | Daniel Martinez | 92804565 | Michael Kumar | 62623673 | Pass | N/A | N/A | Fail | Fail |  |  |  |  | Needs Improvement | AR-2024997 | F-130 |  | TRUE | FALSE | TRUE | Operating Committee |  |  | Financial Reporting Control, CCAR Control | 2024-07-02 |  | 2024-09-02 | 2024-04-15 |  | Status update as of 2024-07-21. Remediation activities progressing. | 2024-07-21 | Patricia Miller | 53737494 | N10122, N20213, N40213 | Options Trading, Trust Services, DevOps | 4200, 2210 | UBS AG Singapore Branch, UBS Europe SE Frankfurt | CTRL-9285415473, CTRL-8934927891 | ISSUE-1939042955, ISSUE-2149938334 | Cyber and Information Security, Data Management
ISSUE-8987073217 | Audit Finding - Data Quality Control Weakness - Group Functions | Audit | Internal audit identified that Outsourcing Risk controls are not operating effectively. Testing revealed gaps in execution and documentation. | Organizational changes affecting ownership | Increased error rates in processing | Increased scrutiny from regulators | All Outsourcing Risk controls operating effectively with documented evidence and no exceptions. | Open | Red | Issue Mitigation Date at significant risk. Key dependencies delayed and remediation plan requires revision. | 2025-02-18 | 2025-02-18 | 0 | 2 | 4 | 4 | 2024-09-23 | 2025-04-19 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | William Miller | 90048179 | Thomas Chen | 76343171 | Sophia Garcia |  | Lucas Smith | 29693143 | Charlotte Young | 81303949 | Fail | Fail | N/A | N/A | Fail |  |  |  |  | Satisfactory | AR-2023843 | F-797 |  | FALSE | FALSE | FALSE | Executive Committee |  | 2024-04-01 | Key Control, Manual Control, IT General Control | 2024-09-23 |  | 2024-12-16 |  |  | Status update as of 2025-04-19. Remediation activities progressing. | 2025-04-19 | Lucas Weber | 18376603 | N40313, N10112 | Transaction Monitoring, Electronic Trading | 4100 | UBS AG Hong Kong Branch | CTRL-4131575764 | ISSUE-9573276057 | Outsourcing Risk
ISSUE-7146318035 | Internal Audit Observation - Monitoring Control Gap - Investment Bank | Audit | Internal audit identified that Organizational Culture controls are not operating effectively. Testing revealed gaps in execution and documentation. | Lack of automated controls and manual workarounds | Documentation gaps and missing evidence | Client complaints and relationship impact | All Organizational Culture controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2022-08-08 | 2022-08-08 | 0 | 0 | 5 | 4 | 2022-01-10 | 2025-06-26 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Kevin Moore | 72306017 | Harper Schmidt | 17122803 |  | 73674613 | Susan Anderson | 31442569 | Oliver Brown | 96551756 | Fail | Fail | Pass | Fail | Fail |  |  |  |  | Needs Improvement | AR-2025527 | F-924 |  | FALSE | TRUE | TRUE | Risk Committee | Business priority assessment completed. |  | Application Control | 2022-01-10 |  | 2022-03-13 | 2024-04-28 | 2024-03-13 | Status update as of 2025-06-26. Remediation activities progressing. | 2025-06-26 | Evelyn Young | 89551741 | N30113, N40113, N20113 | Portfolio Management, Control Testing, Investment Advisory | 4100, 2210, 2100 | UBS AG Hong Kong Branch, UBS Europe SE Frankfurt, UBS AG London Branch | CTRL-4026113008, CTRL-7825844140, CTRL-9786748825 | ISSUE-7805745017 | Organizational Culture
ISSUE-4131356954 | Internal Audit Finding - Control Design Deficiency - Group Functions | Audit | Internal audit identified that Regulatory Change controls are not operating effectively. Testing revealed gaps in execution and documentation. | Legacy systems limitations | Increased error rates in processing | Client complaints and relationship impact | All Regulatory Change controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2023-08-27 | 2023-08-27 | 0 | 0 | 1 | 4 | 2023-03-23 | 2024-09-01 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Henry King | 86555214 | Nancy Johnson | 71047698 |  |  | Patricia Anderson | 59716992 | Barbara Smith | 94195455 | Pass | Fail | N/A | Fail | N/A |  |  |  |  | Satisfactory | AR-2024215 | F-536 |  | FALSE | TRUE | TRUE | Operating Committee |  |  | Financial Reporting Control, Key Control, SOX Control | 2023-03-23 |  | 2023-05-16 | 2025-01-09 |  | Status update as of 2024-09-01. Remediation activities progressing. | 2024-09-01 | Barbara Williams | 59066128 | N14963, N40313 | Deal Execution, Transaction Monitoring | 2210, 3200, 4100 | UBS Europe SE Frankfurt, UBS Financial Services Inc, UBS AG Hong Kong Branch | CTRL-2445662585, CTRL-6649827836 |  | Regulatory Change, Financial Crime Prevention
ISSUE-1422701550 | Audit Issue - Segregation of Duties Weakness - Investment Bank | Audit | Internal audit identified that Financial Crime Prevention controls are not operating effectively. Testing revealed gaps in execution and documentation. | Lack of automated controls and manual workarounds | Documentation gaps and missing evidence | Increased scrutiny from regulators | All Financial Crime Prevention controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2025-01-02 | 2025-01-02 | 0 | 1 | 5 | 4 | 2024-05-16 | 2025-01-16 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Kevin Weber | 70663511 | Margaret Kumar | 18808386 |  | 21718382 | Isabella Harris | 33999716 | David Jones | 24678711 | Pass | Fail | Pass | N/A | Pass |  |  |  |  | Needs Improvement | AR-2023617 | F-995 |  | TRUE | TRUE | FALSE | Executive Committee | Business priority assessment completed. |  | Application Control | 2024-05-16 |  | 2024-07-07 |  |  | Status update as of 2025-01-16. Remediation activities progressing. | 2025-01-16 | Christopher Young | 96528081 | N20213 | Trust Services | 2210 | UBS Europe SE Frankfurt | CTRL-4026113008 | ISSUE-1470939445, ISSUE-9957813353 | Financial Crime Prevention
ISSUE-2926780541 | Audit Issue - Access Management Deficiency - Investment Bank | Audit | Internal audit identified that Third Party Management controls are not operating effectively. Testing revealed gaps in execution and documentation. | Insufficient training and awareness among staff | Delayed or incomplete reporting | Reputational damage to the firm | All Third Party Management controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-08-12 | 2025-01-23 | 1 | 1 | 4 | 3 | 2023-09-14 | 2024-12-09 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Sarah Martin | 33473742 | Karen King | 86224438 | Lucas Taylor |  | Thomas Weber | 84338760 | Susan Williams | 50532800 | N/A | Fail | Fail | N/A | N/A |  |  |  |  | Needs Improvement | AR-2023920 | F-127 |  | TRUE | TRUE | FALSE | Operating Committee | Business priority assessment completed. |  | SOX Control, Regulatory Control | 2023-09-14 |  | 2023-11-09 |  |  | Status update as of 2024-12-09. Remediation activities progressing. | 2024-12-09 | Amelia Lopez | 96541691 | N10112 | Electronic Trading | 3200 | UBS Financial Services Inc | CTRL-1939042955, CTRL-3361388464, CTRL-1817804383, CTRL-2970753705 |  | Third Party Management, Operational Resilience
ISSUE-6491309593 | Audit Issue - Access Management Deficiency - Group Functions | Audit | Internal audit identified that Physical Security controls are not operating effectively. Testing revealed gaps in execution and documentation. | Organizational changes affecting ownership | Control exceptions not properly escalated | Increased scrutiny from regulators | All Physical Security controls operating effectively with documented evidence and no exceptions. | Open | Red | Issue Mitigation Date at significant risk. Key dependencies delayed and remediation plan requires revision. | 2023-06-21 | 2023-06-21 | 0 | 1 | 1 | 4 | 2022-08-22 | 2024-03-19 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Maria Rodriguez | 69315901 | Edward Wang | 33113253 | Emma Davis |  | Charlotte Moore | 51262331 | Lucas Thomas | 27477597 | Pass | Fail | N/A | Pass | Pass |  |  |  |  | Satisfactory | AR-2024984 | F-875 |  | FALSE | TRUE | TRUE | Risk Committee |  |  | Key Control, Application Control, SOX Control | 2022-08-22 |  | 2022-11-18 |  |  | Status update as of 2024-03-19. Remediation activities progressing. | 2024-03-19 | Michael Williams | 18891570 | N10112, N10122 | Electronic Trading, Options Trading | 3100 | UBS Securities LLC | CTRL-8429141456, CTRL-3710566582 |  | Physical Security
ISSUE-4965395580 | Audit Issue - Segregation of Duties Weakness - Investment Bank | Audit | Internal audit identified that Operational Resilience controls are not operating effectively. Testing revealed gaps in execution and documentation. | Inadequate process documentation and procedures | Control exceptions not properly escalated | Increased scrutiny from regulators | All Operational Resilience controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-04-23 | 2024-04-23 | 0 | 0 | 1 | 5 | 2023-05-11 | 2024-04-11 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | David Wilson | 82091897 | James Miller | 38724658 | Andrew Kumar | 34847161 | Matthew Miller | 34273079 | [11 empty] | Needs Improvement | AR-2024555 | F-534 |  | TRUE | TRUE | FALSE | Risk Committee |  |  | SOX Control, Manual Control | 2023-05-11 |  | 2023-06-18 | 2025-05-22 |  | Status update as of 2024-04-11. Remediation activities progressing. | 2024-04-11 | Maria Weber | 84777007 | N10112, N10122, N30113 | Electronic Trading, Options Trading, Portfolio Management | 2210, 3100 | UBS Europe SE Frankfurt, UBS Securities LLC | CTRL-4095476665, CTRL-3361388464, CTRL-8763140509 |  | Operational Resilience, Market Conduct
ISSUE-9807209816 | Internal Audit Observation - Monitoring Control Gap - Asset Management | Audit | Internal audit identified that Talent and Resource Management controls are not operating effectively. Testing revealed gaps in execution and documentation. | Insufficient training and awareness among staff | Control exceptions not properly escalated | Client complaints and relationship impact | All Talent and Resource Management controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2025-02-21 | 2025-02-21 | 0 | 3 | 3 | 5 | 2024-08-12 | 2025-05-24 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Oliver Thompson | 25989909 | Thomas Young | 52219420 | Matthew King |  | Amelia Fischer | 32031067 | [11 empty] | Needs Improvement | AR-2024765 | F-237 |  | FALSE | FALSE | FALSE | Risk Committee |  |  | Manual Control, Application Control, Automated Control | 2024-08-12 |  | 2024-10-16 |  |  | Status update as of 2025-05-24. Remediation activities progressing. | 2025-05-24 | Henry Brown | 62530781 | N40213, N40113 | DevOps, Control Testing | 4100, 4200, 1000 | UBS AG Hong Kong Branch, UBS AG Singapore Branch, UBS AG Zurich | CTRL-1127978094, CTRL-1958682846, CTRL-4289233844 |  | Talent and Resource Management, Technology Change Management
ISSUE-4645120421 | Internal Audit Finding - Reconciliation Control Failure - Global Wealth Management | Audit | Internal audit identified that Regulatory Change controls are not operating effectively. Testing revealed gaps in execution and documentation. | Resource constraints and competing priorities | Increased error rates in processing | Reputational damage to the firm | All Regulatory Change controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2023-07-10 | 2023-07-10 | 0 | 0 | 3 | 5 | 2022-11-23 | 2024-09-21 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20100 | Ultra High Net Worth | N20110 | Private Banking | N20111 | Client Advisory | N20112 | Portfolio Management | N20113 | Investment Advisory | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3200 | UBS Financial Services Inc | Susan Johnson | 17425900 | Isabella Chen | 90745350 |  |  | Christopher Kumar | 98238841 | Isabella Harris | 28865664 | Pass | Pass | N/A | N/A | N/A |  |  |  |  | Satisfactory | AR-2025138 | F-780 |  | FALSE | FALSE | TRUE | Audit Committee |  |  | Financial Reporting Control, IT General Control | 2022-11-23 |  | 2023-02-12 | 2024-08-29 |  | Status update as of 2024-09-21. Remediation activities progressing. | 2024-09-21 | Linda Thomas | 29364653 | N14963 | Deal Execution | 3200 | UBS Financial Services Inc | CTRL-1470939445, CTRL-6488854841, CTRL-4289233844, CTRL-1127978094 |  | Regulatory Change, Physical Security
ISSUE-7380780055 | Audit Issue - Segregation of Duties Weakness - Investment Bank | Audit | Internal audit identified that Intragroup Dependencies controls are not operating effectively. Testing revealed gaps in execution and documentation. | Lack of automated controls and manual workarounds | Control exceptions not properly escalated | Potential regulatory sanctions or fines | All Intragroup Dependencies controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2023-02-01 | 2023-02-01 | 0 | 0 | 2 | 5 | 2022-08-15 | 2025-12-31 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SB | UK & Ireland | C782 | United Kingdom | 2100 | UBS AG London Branch | Robert Young | 74205127 | Lucas Mueller | 33283960 | Robert Weber |  | Christopher Kumar | 34412762 | Patricia White | 86556525 | Pass | Pass | Pass | N/A | N/A |  |  |  |  | Unsatisfactory | AR-2025567 | F-334 |  | TRUE | FALSE | TRUE | Operating Committee |  |  | Automated Control, IT General Control | 2022-08-15 |  | 2022-10-22 | 2024-09-23 | 2024-06-01 | Status update as of 2025-12-31. Remediation activities progressing. | 2025-12-31 | Isabella Kumar | 32833506 | N10122, N10112, N40113 | Options Trading, Electronic Trading, Control Testing | 4300, 2100 | UBS Securities Japan Co Ltd, UBS AG London Branch | CTRL-8168204967, CTRL-7665963761 |  | Intragroup Dependencies, Organizational Culture
ISSUE-2627677155 | Internal Audit Finding - Control Design Deficiency - Investment Bank | Audit | Internal audit identified that Conduct Risk controls are not operating effectively. Testing revealed gaps in execution and documentation. | Inadequate process documentation and procedures | Inconsistent application of procedures | Financial losses from operational errors | All Conduct Risk controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-11-14 | 2024-11-14 | 0 | 1 | 3 | 4 | 2024-01-09 | 2024-09-26 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3200 | UBS Financial Services Inc | Robert Lopez | 30302410 | Karen Young | 17143361 |  |  | Amelia Williams | 73115555 | Michael Wilson | 72697508 | Fail | Pass | Fail | Pass | Fail |  |  |  |  | Needs Improvement | AR-2025905 | F-674 |  | FALSE | FALSE | FALSE | Risk Committee | Business priority assessment completed. |  | Financial Reporting Control | 2024-01-09 |  | 2024-02-13 | 2024-07-27 |  | Status update as of 2024-09-26. Remediation activities progressing. | 2024-09-26 | David Anderson | 32588172 | N40313, N20213, N20113 | Transaction Monitoring, Trust Services, Investment Advisory | 2100, 3200, 4200 | UBS AG London Branch, UBS Financial Services Inc, UBS AG Singapore Branch | CTRL-3694860228, CTRL-9703905715 |  | Conduct Risk
ISSUE-1664847319 | Audit Finding - Data Quality Control Weakness - Group Functions | Audit | Internal audit identified that Operational Resilience controls are not operating effectively. Testing revealed gaps in execution and documentation. | Legacy systems limitations | Documentation gaps and missing evidence | Potential regulatory sanctions or fines | All Operational Resilience controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2025-07-16 | 2025-07-16 | 0 | 0 | 4 | 5 | 2024-09-25 | 2025-08-28 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Emma Thompson | 87363548 | Robert Jones | 45950066 | Christopher Wright |  | Margaret Li | 70173215 | [11 empty] | Unsatisfactory | AR-2024787 | F-121 |  | TRUE | FALSE | TRUE | Executive Committee |  |  | Automated Control | 2024-09-25 |  | 2024-12-22 | 2025-12-02 |  | Status update as of 2025-08-28. Remediation activities progressing. | 2025-08-28 | Elizabeth King | 27603804 | N40113, N40413 | Control Testing, Capital Calculations | 4100, 4200, 3100 | UBS AG Hong Kong Branch, UBS AG Singapore Branch, UBS Securities LLC | CTRL-7517938612, CTRL-7665963761 |  | Operational Resilience, Talent and Resource Management
ISSUE-2274350418 | Audit Observation - Process Documentation Gaps - Investment Bank | Audit | Internal audit identified that Outsourcing Risk controls are not operating effectively. Testing revealed gaps in execution and documentation. | Inadequate process documentation and procedures | Control exceptions not properly escalated | Client complaints and relationship impact | All Outsourcing Risk controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2023-05-24 | 2023-10-27 | 1 | 1 | 1 | 4 | 2022-07-26 | 2024-11-06 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Henry Anderson | 77575794 | Oliver Jones | 55329991 |  | 26198473 | Karen Moore | 75278845 | Michael Wang | 57679636 | Pass | N/A | Fail | Pass | N/A |  |  |  |  | Unsatisfactory | AR-2025476 | F-785 |  | TRUE | TRUE | FALSE | Executive Committee | Business priority assessment completed. |  | Automated Control | 2022-07-26 |  | 2022-10-03 |  |  | Status update as of 2024-11-06. Remediation activities progressing. | 2024-11-06 | Benjamin Williams | 78089422 | N14963 | Deal Execution | 2210, 4200, 4300 | UBS Europe SE Frankfurt, UBS AG Singapore Branch, UBS Securities Japan Co Ltd | CTRL-8934927891, CTRL-8664882079, CTRL-5996775663 | ISSUE-8664882079, ISSUE-6009268066 | Outsourcing Risk
ISSUE-5160575046 | Internal Audit Observation - Monitoring Control Gap - Asset Management | Audit | Internal audit identified that Technology Change Management controls are not operating effectively. Testing revealed gaps in execution and documentation. | Inadequate process documentation and procedures | Inconsistent application of procedures | Client complaints and relationship impact | All Technology Change Management controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2022-08-17 | 2023-01-15 | 1 | 2 | 3 | 5 | 2022-01-14 | 2024-12-15 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Maria Jackson | 30348912 | Jessica Martin | 40626070 |  |  | Christopher King | 79277190 | Maria Johnson | 69401906 | Pass | Pass | N/A | N/A | Pass |  |  |  |  | Satisfactory | AR-2024386 | F-422 |  | FALSE | TRUE | FALSE | Risk Committee |  |  | CCAR Control, Key Control, Regulatory Control | 2022-01-14 |  | 2022-03-11 |  |  | Status update as of 2024-12-15. Remediation activities progressing. | 2024-12-15 | Patricia Fischer | 52103461 | N10112, N20213 | Electronic Trading, Trust Services | 1000, 4100, 3100 | UBS AG Zurich, UBS AG Hong Kong Branch, UBS Securities LLC | CTRL-2452066459, CTRL-7665963761, CTRL-1083651970, CTRL-7517938612 | ISSUE-9894264595, ISSUE-2351531223 | Technology Change Management
ISSUE-3555656321 | Internal Audit Finding - Reconciliation Control Failure - Group Functions | Audit | Internal audit identified that Operational Resilience controls are not operating effectively. Testing revealed gaps in execution and documentation. | Inadequate process documentation and procedures | Control exceptions not properly escalated | Reputational damage to the firm | All Operational Resilience controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2023-04-28 | 2023-04-28 | 0 | 2 | 2 | 3 | 2022-12-26 | 2024-03-07 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Emma Mueller | 85177493 | Barbara Smith | 67326334 | Sophia Chen |  | Christopher Schmidt | 26336672 | Jessica King | 76514912 | Fail | N/A | Pass | N/A | Pass |  |  |  |  | Satisfactory | AR-2024139 | F-530 |  | FALSE | FALSE | TRUE | Executive Committee |  |  | Key Control, BCBS239 Control, IT General Control | 2022-12-26 |  | 2023-01-29 |  |  | Status update as of 2024-03-07. Remediation activities progressing. | 2024-03-07 | Evelyn Taylor | 32076343 | N20213, N10122 | Trust Services, Options Trading | 2210, 2100, 3100 | UBS Europe SE Frankfurt, UBS AG London Branch, UBS Securities LLC | CTRL-1958682846, CTRL-4289233844, CTRL-1519709079, CTRL-6649827836 | ISSUE-4460967357 | Operational Resilience, Business Continuity
ISSUE-3553440342 | Internal Audit Finding - Control Design Deficiency - Investment Bank | Audit | Internal audit identified that Cyber and Information Security controls are not operating effectively. Testing revealed gaps in execution and documentation. | Inadequate process documentation and procedures | Documentation gaps and missing evidence | Increased scrutiny from regulators | All Cyber and Information Security controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2025-05-29 | 2025-09-27 | 1 | 1 | 2 | 4 | 2024-06-11 | 2024-11-14 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Elizabeth Weber | 59503523 | James Martinez | 17693044 |  | 85088096 | Sophia Thompson | 56146216 | Alexander Taylor | 95973808 | Pass | Pass | Fail | Pass | N/A |  |  |  |  | Needs Improvement | AR-2025846 | F-808 |  | FALSE | FALSE | FALSE | Operating Committee |  |  | Key Control, Application Control | 2024-06-11 |  | 2024-07-25 |  |  | Status update as of 2024-11-14. Remediation activities progressing. | 2024-11-14 | James Moore | 40906854 | N40413, N20113 | Capital Calculations, Investment Advisory | 4300 | UBS Securities Japan Co Ltd | CTRL-8763140509, CTRL-7805745017, CTRL-7665963761 |  | Cyber and Information Security
ISSUE-7540301973 | Internal Audit Observation - Monitoring Control Gap - Asset Management | Audit | Internal audit identified that Cyber and Information Security controls are not operating effectively. Testing revealed gaps in execution and documentation. | Legacy systems limitations | Control exceptions not properly escalated | Reputational damage to the firm | All Cyber and Information Security controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-02-08 | 2024-02-08 | 0 | 0 | 3 | 5 | 2023-08-26 | 2024-02-24 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Susan Thomas | 20926356 | Andrew Jones | 32472549 | Joshua Kumar |  | Barbara Anderson | 53194369 | Maria Wright | 76409861 | Fail | Fail | N/A | Fail | N/A |  |  |  |  | Unsatisfactory | AR-2025662 | F-137 |  | TRUE | TRUE | TRUE | Executive Committee | Business priority assessment completed. |  | IT General Control, Automated Control | 2023-08-26 |  | 2023-10-31 | 2024-06-09 |  | Status update as of 2024-02-24. Remediation activities progressing. | 2024-02-24 | Maria Mueller | 83893835 | N14963 | Deal Execution | 3200 | UBS Financial Services Inc | CTRL-4274958945, CTRL-8110054933, CTRL-4026113008, CTRL-9957813353 |  | Cyber and Information Security
ISSUE-9309500117 | Internal Audit Finding - Reconciliation Control Failure - Group Functions | Audit | Internal audit identified that Legal Risk controls are not operating effectively. Testing revealed gaps in execution and documentation. | Lack of automated controls and manual workarounds | Inconsistent application of procedures | Financial losses from operational errors | All Legal Risk controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-04-24 | 2024-04-24 | 0 | 1 | 3 | 4 | 2023-07-14 | 2025-03-28 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Joshua Garcia | 47101128 | Daniel Miller | 25916596 |  |  | Alexander Wang | 36393422 | Elizabeth Mueller | 50629797 | N/A | N/A | Fail | Pass | N/A |  |  |  |  | Unsatisfactory | AR-2023565 | F-975 |  | FALSE | TRUE | FALSE | Operating Committee | Business priority assessment completed. |  | IT General Control, Key Control | 2023-07-14 |  | 2023-09-12 |  |  | Status update as of 2025-03-28. Remediation activities progressing. | 2025-03-28 | Joshua Martinez | 63352256 | N20113 | Investment Advisory | 3100, 4300, 2210 | UBS Securities LLC, UBS Securities Japan Co Ltd, UBS Europe SE Frankfurt | CTRL-3030106617, CTRL-8047877267, CTRL-2149938334, CTRL-7635473142 |  | Legal Risk, Regulatory Compliance
ISSUE-2699887270 | Audit Observation - Process Documentation Gaps - Group Functions | Audit | Internal audit identified that Client Suitability controls are not operating effectively. Testing revealed gaps in execution and documentation. | Organizational changes affecting ownership | Control exceptions not properly escalated | Potential regulatory sanctions or fines | All Client Suitability controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-07-06 | 2024-07-06 | 0 | 3 | 3 | 3 | 2024-03-16 | 2024-06-10 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40400 | Group Finance | N40410 | Financial Reporting | N40411 | Regulatory Reporting | N40412 | Capital Reporting | N40413 | Capital Calculations | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Harper Lopez | 65200819 | Karen Davis | 59490380 |  |  | Robert Martin | 70523603 | Henry Mueller | 37833011 | N/A | Pass | Fail | Pass | Pass |  |  |  |  | Unsatisfactory | AR-2025845 | F-791 |  | FALSE | FALSE | FALSE | Executive Committee | Business priority assessment completed. |  | Regulatory Control | 2024-03-16 |  | 2024-04-22 |  |  | Status update as of 2024-06-10. Remediation activities progressing. | 2024-06-10 | Lucas Chen | 99965548 | N40213, N40413, N40313 | DevOps, Capital Calculations, Transaction Monitoring | 2210 | UBS Europe SE Frankfurt | CTRL-8168204967, CTRL-7567496105 |  | Client Suitability, Process Execution
ISSUE-6583444930 | Audit Issue - Access Management Deficiency - Global Wealth Management | Audit | Internal audit identified that Technology Production Stability controls are not operating effectively. Testing revealed gaps in execution and documentation. | Insufficient training and awareness among staff | Delayed or incomplete reporting | Financial losses from operational errors | All Technology Production Stability controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2023-09-10 | 2023-11-22 | 1 | 1 | 1 | 3 | 2022-09-12 | 2024-03-20 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20200 | High Net Worth | N20210 | Wealth Planning | N20211 | Tax Advisory | N20212 | Estate Planning | N20213 | Trust Services | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Amelia Thomas | 14623108 | Kevin Thomas | 69332039 | Jessica Miller |  | Jennifer Young | 17035056 | Edward Smith | 16531664 | Fail | Pass | Pass | Fail | Pass |  |  |  |  | Satisfactory | AR-2023375 | F-116 |  | FALSE | TRUE | TRUE | Operating Committee | Business priority assessment completed. |  | BCBS239 Control | 2022-09-12 |  | 2022-12-07 | 2024-04-08 |  | Status update as of 2024-03-20. Remediation activities progressing. | 2024-03-20 | Henry Wilson | 15907259 | N40313, N10122 | Transaction Monitoring, Options Trading | 4100, 3200 | UBS AG Hong Kong Branch, UBS Financial Services Inc | CTRL-7517938612, CTRL-7665963761 | ISSUE-5161807235, ISSUE-9786748825 | Technology Production Stability
ISSUE-8316648259 | Internal Audit Finding - Control Design Deficiency - Group Functions | Audit | Internal audit identified that Operational Resilience controls are not operating effectively. Testing revealed gaps in execution and documentation. | Lack of automated controls and manual workarounds | Increased error rates in processing | Increased scrutiny from regulators | All Operational Resilience controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2023-11-07 | 2023-12-12 | 1 | 4 | 5 | 3 | 2023-01-14 | 2025-02-07 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Nancy Davis | 37845315 | Mia Anderson | 90410190 | James Young | 26514861 | Oliver Rodriguez | 87186069 | Harper Wilson | 21787125 | N/A | Fail | Pass | Pass | Pass |  |  |  |  | Unsatisfactory | AR-2024223 | F-472 |  | TRUE | FALSE | TRUE | Audit Committee |  | 2025-06-15 | Manual Control, Application Control | 2023-01-14 |  | 2023-02-21 |  |  | Status update as of 2025-02-07. Remediation activities progressing. | 2025-02-07 | Brian Lopez | 52001565 | N30113, N40313, N20113 | Portfolio Management, Transaction Monitoring, Investment Advisory | 2210, 4100, 2100 | UBS Europe SE Frankfurt, UBS AG Hong Kong Branch, UBS AG London Branch | CTRL-4163119785, CTRL-3303082117 |  | Operational Resilience, Third Party Management
ISSUE-3849232839 | Audit Observation - Process Documentation Gaps - Group Functions | Audit | Internal audit identified that Cyber and Information Security controls are not operating effectively. Testing revealed gaps in execution and documentation. | Lack of automated controls and manual workarounds | Inconsistent application of procedures | Reputational damage to the firm | All Cyber and Information Security controls operating effectively with documented evidence and no exceptions. | Open | Red | Issue Mitigation Date at significant risk. Key dependencies delayed and remediation plan requires revision. | 2024-12-04 | 2024-12-04 | 0 | 1 | 1 | 5 | 2023-12-08 | 2025-02-16 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3200 | UBS Financial Services Inc | Thomas Schmidt | 17095369 | Maria Jackson | 91698732 |  |  | Matthew Li | 72903261 | [11 empty] | Unsatisfactory | AR-2024175 | F-382 |  | FALSE | TRUE | FALSE | Risk Committee | Business priority assessment completed. |  | SOX Control, Automated Control | 2023-12-08 |  | 2024-01-11 |  |  | Status update as of 2025-02-16. Remediation activities progressing. | 2025-02-16 | Evelyn Garcia | 32161108 | N10112, N10122, N20213 | Electronic Trading, Options Trading, Trust Services | 4300, 4200, 2100 | UBS Securities Japan Co Ltd, UBS AG Singapore Branch, UBS AG London Branch | CTRL-1983297492, CTRL-5951406973, CTRL-8664882079, CTRL-2445662585 |  | Cyber and Information Security
ISSUE-5871743247 | Audit Observation - Process Documentation Gaps - Group Functions | Audit | Internal audit identified that Technology Production Stability controls are not operating effectively. Testing revealed gaps in execution and documentation. | Organizational changes affecting ownership | Increased error rates in processing | Client complaints and relationship impact | All Technology Production Stability controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2025-09-22 | 2025-09-22 | 0 | 0 | 5 | 5 | 2024-12-30 | 2025-11-08 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Edward Young | 32620027 | Jessica Moore | 33463164 |  | 78945564 | John Brown | 66736822 | Susan White | 32881970 | Fail | Pass | Fail | N/A | Pass |  |  |  |  | Unsatisfactory | AR-2023483 | F-397 |  | FALSE | FALSE | FALSE | Operating Committee |  |  | IT General Control, BCBS239 Control, Regulatory Control | 2024-12-30 |  | 2025-03-29 | 2025-10-20 | 2025-06-11 | Status update as of 2025-11-08. Remediation activities progressing. | 2025-11-08 | Oliver King | 92912825 | N10112, N30113 | Electronic Trading, Portfolio Management | 4300 | UBS Securities Japan Co Ltd | CTRL-6924716023, CTRL-8110054933, CTRL-4460967357 |  | Technology Production Stability, Talent and Resource Management