## Sheet1
issue_id | issue_title | issue_type | control_deficiency | root_cause | symptoms | risk_description | success_criteria | issue_status | issue_rag_status | issue_rag_justification | original_mitigation_date | current_mitigation_date | mitigation_date_change_count | open_action_plans | total_action_plans | severity_rating | created_on | last_modified_on | group_id | group_name | division_id | division_name | unit_id | unit_name | area_id | area_name | sector_id | sector_name | segment_id | segment_name | function_id | function_name | l0_location_id | l0_location_name | region_id | region_name | sub_region_id | sub_region_name | country_id | country_name | company_id | company_short_name | issue_owner | issue_owner_gpn | issue_administrator | issue_administrator_gpn | issue_delegate | issue_delegate_gpn | first_level_reviewer | first_level_reviewer_gpn | orc_reviewer | orc_reviewer_gpn | orc_articulation_check | orc_rating_check | orc_mitigation_date_check | orc_action_plan_check | orc_mapping_check | regulatory_manager | regulatory_manager_gpn | regulator_country | regulator_type | audit_rating | audit_report_id | finding_id | mra_mria | dsori_program | gsori_program | eandy_relevant | operating_committee | reprioritization_risk_acceptance_justification | risk_acceptance_approval_date | category_flags | draft_date | open_grace_period_date | open_date | completed_date | closed_date | last_comment | last_comment_date | last_commenter | last_commenter_gpn | related_function_ids | related_function_names | related_location_ids | related_location_names | linked_control_ids | related_issue_ids | risk_themes
ISSUE-2181241943 | Regulatory Finding - Capital Calculation Error - Group Functions | Regulatory | Regulatory examination identified deficiencies in Third Party Management compliance that require immediate attention. | Insufficient training and awareness among staff | Inconsistent application of procedures | Increased scrutiny from regulators | All Third Party Management controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2022-07-07 | 2022-07-07 | 0 | 0 | 2 | 3 | 2022-02-25 | 2024-05-18 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Robert Thomas | 71028710 | Robert Wang | 60885459 |  | 66581473 | Michael Garcia | 73123515 | [7 empty] | Emma Brown | 56970882 | Switzerland | FINMA |  |  |  |  | TRUE | TRUE | TRUE | Audit Committee |  |  | BCBS239 Control | 2022-02-25 |  | 2022-04-04 | 2025-04-29 | 2025-11-16 | Status update as of 2024-05-18. Remediation activities progressing. | 2024-05-18 | Mia Thomas | 72415804 | N20213, N30113, N14963 | Trust Services, Portfolio Management, Deal Execution | 2210, 4200, 4300 | UBS Europe SE Frankfurt, UBS AG Singapore Branch, UBS Securities Japan Co Ltd | CTRL-4460967357, CTRL-9957813353, CTRL-1958682846 | ISSUE-9697354961, ISSUE-3746317213 | Third Party Management, Talent and Resource Management
ISSUE-4163119785 | Regulatory Examination Finding - Compliance Gap - Global Wealth Management | Regulatory | Regulatory examination identified deficiencies in Legal Risk compliance that require immediate attention. | Lack of automated controls and manual workarounds | Delayed or incomplete reporting | Client complaints and relationship impact | All Legal Risk controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-01-15 | 2024-01-15 | 0 | 3 | 4 | 4 | 2023-05-14 | 2025-01-12 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20100 | Ultra High Net Worth | N20110 | Private Banking | N20111 | Client Advisory | N20112 | Portfolio Management | N20113 | Investment Advisory | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Sarah Fischer | 43742830 | Daniel Davis | 35848226 |  | 34850391 | Alexander Thomas | 74988034 | Sarah Weber | 23492385 | Pass | Fail | Pass | Fail | Pass | Jennifer Smith | 81690398 | Japan | FSA Japan |  |  |  | MRIA | TRUE | TRUE | FALSE | Audit Committee |  |  | Key Control | 2023-05-14 |  | 2023-07-19 |  |  | Status update as of 2025-01-12. Remediation activities progressing. | 2025-01-12 | David Wright | 74251933 | N30113, N14963 | Portfolio Management, Deal Execution | 3200 | UBS Financial Services Inc | CTRL-8293453178, CTRL-1939042955, CTRL-7483366056, CTRL-2948728483 |  | Legal Risk, Technology Production Stability
ISSUE-1127978094 | Regulatory Matter - Customer Protection Issue - Group Functions | Regulatory | Regulatory examination identified deficiencies in Legal Risk compliance that require immediate attention. | Insufficient training and awareness among staff | Increased error rates in processing | Increased scrutiny from regulators | All Legal Risk controls operating effectively with documented evidence and no exceptions. | Open | Red | Issue Mitigation Date at significant risk. Key dependencies delayed and remediation plan requires revision. | 2023-10-24 | 2023-10-24 | 0 | 1 | 1 | 3 | 2023-05-06 | 2024-01-15 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Charlotte Lopez | 49172995 | Joshua Schmidt | 65766169 | Andrew Jackson |  | Charlotte White | 35583290 | Edward Rodriguez | 19369750 | Fail | Fail | Fail | N/A | Fail | James Weber | 50071487 | Switzerland | FINMA |  |  |  | MRA | FALSE | FALSE | FALSE | Operating Committee |  |  | Financial Reporting Control, BCBS239 Control | 2023-05-06 |  | 2023-07-19 |  |  | Status update as of 2024-01-15. Remediation activities progressing. | 2024-01-15 | Evelyn White | 41348220 | N10112, N30113 | Electronic Trading, Portfolio Management | 4300, 4100, 3100 | UBS Securities Japan Co Ltd, UBS AG Hong Kong Branch, UBS Securities LLC | CTRL-9894847574, CTRL-1945826486, CTRL-5710360983, CTRL-4919706735 | ISSUE-4163119785 | Legal Risk, Transaction Processing
ISSUE-8293453178 | Regulatory Matter - Customer Protection Issue - Group Functions | Regulatory | Regulatory examination identified deficiencies in Process Execution compliance that require immediate attention. | Legacy systems limitations | Documentation gaps and missing evidence | Potential regulatory sanctions or fines | All Process Execution controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-01-14 | 2024-02-27 | 1 | 2 | 2 | 4 | 2023-03-28 | 2024-01-08 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | James Lopez | 67801537 | Amelia Rodriguez | 61030579 | Daniel Li |  | Oliver Thompson | 12515446 | Barbara Jones | 52018286 | N/A | Fail | N/A | Fail | N/A | Christopher Weber | 25458308 | Germany | Bundesbank |  |  |  | MRA | FALSE | TRUE | FALSE | Operating Committee |  |  | IT General Control | 2023-03-28 |  | 2023-06-03 |  |  | Status update as of 2024-01-08. Remediation activities progressing. | 2024-01-08 | Patricia Garcia | 63118906 | N30113, N20113 | Portfolio Management, Investment Advisory | 1000, 2100 | UBS AG Zurich, UBS AG London Branch | CTRL-9592390865 |  | Process Execution, Operational Resilience
ISSUE-3303082117 | Examination Finding - AML Control Weakness - Investment Bank | Regulatory | Regulatory examination identified deficiencies in Conduct Risk compliance that require immediate attention. | Inadequate process documentation and procedures | Delayed or incomplete reporting | Increased scrutiny from regulators | All Conduct Risk controls operating effectively with documented evidence and no exceptions. | Draft | Green | Remediation on track. All action plans progressing as planned. | 2025-08-30 | 2025-08-30 | 0 | 4 | 4 | 3 | 2024-11-08 | 2024-02-16 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Joshua Rodriguez | 54018830 | Margaret Chen | 31810655 |  | 50162553 | Nancy Wang | 78090664 | Joshua Lopez | 85554415 | Fail | Fail | Pass | Fail | Fail | Mia Martin | 88343175 | Singapore | MAS |  |  |  |  | TRUE | FALSE | FALSE | Audit Committee |  |  | Manual Control | 2024-11-08 |  |  |  |  | Status update as of 2024-02-16. Remediation activities progressing. | 2024-02-16 | Margaret White | 29834119 | N20113, N10112, N10122 | Investment Advisory, Electronic Trading, Options Trading | 2100 | UBS AG London Branch | CTRL-8235363119, CTRL-3694860228, CTRL-5710360983, CTRL-1470939445 |  | Conduct Risk, Physical Security
ISSUE-2625792787 | Regulatory Issue - Reporting Deficiency - Group Functions | Regulatory | Regulatory examination identified deficiencies in Transaction Processing compliance that require immediate attention. | Legacy systems limitations | Delayed or incomplete reporting | Increased scrutiny from regulators | All Transaction Processing controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2024-09-26 | 2024-09-26 | 0 | 0 | 4 | 5 | 2023-10-28 | 2024-11-17 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | John Mueller | 91883092 | Andrew Taylor | 43087238 |  |  | Jennifer Weber | 37820354 | Susan Chen | 74398125 | Fail | N/A | N/A | Fail | Fail | Mia White | 62953249 | Japan | JFSA |  |  |  | MRA | FALSE | TRUE | FALSE | Risk Committee |  |  | Application Control, BCBS239 Control | 2023-10-28 |  | 2023-12-09 | 2025-07-05 | 2024-10-04 | Status update as of 2024-11-17. Remediation activities progressing. | 2024-11-17 | Karen Schmidt | 28424464 | N40413 | Capital Calculations | 3100, 2210, 2100 | UBS Securities LLC, UBS Europe SE Frankfurt, UBS AG London Branch | CTRL-1965067727, CTRL-4026113008 |  | Transaction Processing
ISSUE-7665963761 | Regulatory Observation - Governance Deficiency - Group Functions | Regulatory | Regulatory examination identified deficiencies in Technology Change Management compliance that require immediate attention. | Inadequate process documentation and procedures | Increased error rates in processing | Increased scrutiny from regulators | All Technology Change Management controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2023-09-14 | 2023-09-14 | 0 | 2 | 3 | 4 | 2022-11-20 | 2025-05-02 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Isabella Moore | 81826922 | Oliver Anderson | 66087572 | Amelia Williams | 63283709 | Susan Anderson | 48851599 | Oliver Smith | 50049524 | N/A | N/A | Pass | Fail | Fail | Barbara Lopez | 28012011 | Hong Kong | HKMA |  |  |  | MRIA | TRUE | TRUE | FALSE | Audit Committee |  |  | CCAR Control, Key Control, Financial Reporting Control | 2022-11-20 |  | 2023-02-08 |  |  | Status update as of 2025-05-02. Remediation activities progressing. | 2025-05-02 | David Taylor | 33554528 | N40113, N40413, N30113 | Control Testing, Capital Calculations, Portfolio Management | 4200 | UBS AG Singapore Branch | CTRL-8429141456 | ISSUE-7635473142, ISSUE-1127978094 | Technology Change Management, Process Execution
ISSUE-3479708607 | Examination Finding - AML Control Weakness - Group Functions | Regulatory | Regulatory examination identified deficiencies in Technology Production Stability compliance that require immediate attention. | Insufficient training and awareness among staff | Delayed or incomplete reporting | Increased scrutiny from regulators | All Technology Production Stability controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2022-09-20 | 2022-09-20 | 0 | 1 | 1 | 3 | 2022-05-30 | 2025-12-18 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Amelia Rodriguez | 96104027 | Christopher Kumar | 61335545 |  | 60666702 | Thomas Garcia | 98824290 | [7 empty] | Kevin Rodriguez | 97715861 | Japan | JFSA |  |  |  | MRA | TRUE | FALSE | TRUE | Audit Committee | Business priority assessment completed. |  | Application Control, Manual Control | 2022-05-30 |  | 2022-07-26 |  |  | Status update as of 2025-12-18. Remediation activities progressing. | 2025-12-18 | Kevin White | 40824989 | N40213 | DevOps | 1000, 4300 | UBS AG Zurich, UBS Securities Japan Co Ltd | CTRL-3030106617, CTRL-7114223633 |  | Technology Production Stability, Client Suitability
ISSUE-4026113008 | Regulatory Examination Finding - Compliance Gap - Group Functions | Regulatory | Regulatory examination identified deficiencies in Intragroup Dependencies compliance that require immediate attention. | Insufficient training and awareness among staff | Control exceptions not properly escalated | Potential regulatory sanctions or fines | All Intragroup Dependencies controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2024-10-25 | 2024-10-25 | 0 | 1 | 2 | 3 | 2024-07-03 | 2024-02-15 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SB | UK & Ireland | C782 | United Kingdom | 2100 | UBS AG London Branch | David Moore | 87324220 | Robert Chen | 41796721 |  |  | Jessica Moore | 65507111 | Jennifer Schmidt | 18181595 | N/A | N/A | N/A | Pass | N/A | Linda Lopez | 16292676 | United Kingdom | PRA |  |  |  |  | FALSE | FALSE | FALSE | Executive Committee |  |  | Application Control, BCBS239 Control, Manual Control | 2024-07-03 |  | 2024-08-21 |  |  | Status update as of 2024-02-15. Remediation activities progressing. | 2024-02-15 | Charlotte King | 17734153 | N40113, N40413, N14963 | Control Testing, Capital Calculations, Deal Execution | 3100, 1000 | UBS Securities LLC, UBS AG Zurich | CTRL-6649827836, CTRL-2452066459 |  | Intragroup Dependencies
ISSUE-9786748825 | Examination Issue - Risk Management Gap - Group Functions | Regulatory | Regulatory examination identified deficiencies in Physical Security compliance that require immediate attention. | Inadequate process documentation and procedures | Increased error rates in processing | Financial losses from operational errors | All Physical Security controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-06-01 | 2024-08-18 | 1 | 0 | 5 | 4 | 2024-02-12 | 2025-08-24 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Elizabeth Fischer | 12058055 | Harper Taylor | 25745913 | Andrew Jackson | 37449289 | Patricia Jackson | 84098828 | [7 empty] | Robert Weber | 61091554 | Hong Kong | HKMA |  |  |  |  | FALSE | FALSE | FALSE | Operating Committee |  |  | Application Control | 2024-02-12 |  | 2024-04-30 | 2024-11-23 |  | Status update as of 2025-08-24. Remediation activities progressing. | 2025-08-24 | Harper Kumar | 51999682 | N10112, N20113 | Electronic Trading, Investment Advisory | 1000, 2100, 4300 | UBS AG Zurich, UBS AG London Branch, UBS Securities Japan Co Ltd | CTRL-5996775663, CTRL-5710360983, CTRL-2625792787, CTRL-6649827836 |  | Physical Security
ISSUE-6488854841 | Regulatory Matter - Customer Protection Issue - Asset Management | Regulatory | Regulatory examination identified deficiencies in Data Management compliance that require immediate attention. | Resource constraints and competing priorities | Control exceptions not properly escalated | Reputational damage to the firm | All Data Management controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2023-12-07 | 2023-12-07 | 0 | 0 | 1 | 4 | 2023-04-08 | 2024-03-23 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3200 | UBS Financial Services Inc | Karen Wright | 17531619 | James Wilson | 21097943 |  |  | Elizabeth Miller | 80888325 | Oliver Moore | 38375916 | N/A | N/A | Fail | Fail | Pass | William Schmidt | 82884346 | United States | CFTC |  |  |  |  | TRUE | TRUE | FALSE | Risk Committee | Business priority assessment completed. |  | IT General Control, SOX Control, Regulatory Control | 2023-04-08 |  | 2023-05-18 | 2025-07-31 |  | Status update as of 2024-03-23. Remediation activities progressing. | 2024-03-23 | Evelyn White | 82553061 | N40113, N14963 | Control Testing, Deal Execution | 2210, 3200, 4100 | UBS Europe SE Frankfurt, UBS Financial Services Inc, UBS AG Hong Kong Branch | CTRL-2812140441, CTRL-7825844140, CTRL-9573276057 |  | Data Management, Market Conduct
ISSUE-6924716023 | Regulatory Examination Finding - Compliance Gap - Investment Bank | Regulatory | Regulatory examination identified deficiencies in Physical Security compliance that require immediate attention. | Legacy systems limitations | Increased error rates in processing | Financial losses from operational errors | All Physical Security controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2024-05-12 | 2024-10-01 | 1 | 2 | 2 | 3 | 2024-01-22 | 2025-07-13 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | John Garcia | 68930964 | Mia Jackson | 38169370 | Nancy Li | 91907952 | Linda Wilson | 92698414 | Lucas Thomas | 37775381 | Pass | N/A | Fail | N/A | Fail | Edward Wilson | 53440052 | Japan | JFSA |  |  |  | MRIA | FALSE | TRUE | TRUE | Executive Committee | Business priority assessment completed. | 2025-11-02 | CCAR Control | 2024-01-22 |  | 2024-03-07 |  |  | Status update as of 2025-07-13. Remediation activities progressing. | 2025-07-13 | Charlotte Chen | 43226234 | N40113, N40213, N14963 | Control Testing, DevOps, Deal Execution | 3200, 4100, 3100 | UBS Financial Services Inc, UBS AG Hong Kong Branch, UBS Securities LLC | CTRL-9639245200, CTRL-9703905715, CTRL-1965067727, CTRL-4131356954 |  | Physical Security, Business Continuity
ISSUE-2137651678 | Regulatory Finding - Capital Calculation Error - Group Functions | Regulatory | Regulatory examination identified deficiencies in Outsourcing Risk compliance that require immediate attention. | Lack of automated controls and manual workarounds | Control exceptions not properly escalated | Reputational damage to the firm | All Outsourcing Risk controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2023-07-12 | 2023-07-12 | 0 | 1 | 2 | 5 | 2022-08-02 | 2024-03-20 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40400 | Group Finance | N40410 | Financial Reporting | N40411 | Regulatory Reporting | N40412 | Capital Reporting | N40413 | Capital Calculations | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Elizabeth Young | 11529494 | Michael Thomas | 43492807 | John Mueller | 10171954 | Sophia White | 68816911 | Christopher Wilson | 65568711 | Fail | Fail | Fail | N/A | Fail | Benjamin Wright | 87585294 | Singapore | MAS |  |  |  | MRA | FALSE | TRUE | TRUE | Operating Committee |  |  | SOX Control | 2022-08-02 |  | 2022-09-22 |  |  | Status update as of 2024-03-20. Remediation activities progressing. | 2024-03-20 | Henry White | 31596235 | N10122, N40313, N40413 | Options Trading, Transaction Monitoring, Capital Calculations | 4300, 4100 | UBS Securities Japan Co Ltd, UBS AG Hong Kong Branch | CTRL-9573276057 | ISSUE-6924716023 | Outsourcing Risk
ISSUE-5284391408 | Regulatory Issue - Reporting Deficiency - Group Functions | Regulatory | Regulatory examination identified deficiencies in Conduct Risk compliance that require immediate attention. | Insufficient training and awareness among staff | Inconsistent application of procedures | Financial losses from operational errors | All Conduct Risk controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-05-12 | 2024-05-12 | 0 | 1 | 1 | 3 | 2024-02-02 | 2024-11-06 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SB | UK & Ireland | C782 | United Kingdom | 2100 | UBS AG London Branch | Matthew Chen | 46160937 | Christopher Garcia | 35224301 |  | 64649480 | Susan Kumar | 17543817 | Joshua Wilson | 18806960 | Fail | N/A | N/A | Fail | Pass | Jessica Johnson | 33318633 | United Kingdom | FCA |  |  |  | MRA | TRUE | TRUE | TRUE | Executive Committee |  |  | Regulatory Control | 2024-02-02 |  | 2024-03-26 |  |  | Status update as of 2024-11-06. Remediation activities progressing. | 2024-11-06 | Barbara Harris | 95283260 | N10112 | Electronic Trading | 4100 | UBS AG Hong Kong Branch | CTRL-3361388464, CTRL-9639245200, CTRL-4466589567, CTRL-5774080233 |  | Conduct Risk, Transaction Processing
ISSUE-1470939445 | Examination Issue - Risk Management Gap - Asset Management | Regulatory | Regulatory examination identified deficiencies in Anti-Money Laundering compliance that require immediate attention. | Organizational changes affecting ownership | Documentation gaps and missing evidence | Reputational damage to the firm | All Anti-Money Laundering controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2023-10-24 | 2023-12-07 | 1 | 1 | 2 | 5 | 2022-11-04 | 2025-09-06 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3200 | UBS Financial Services Inc | David Mueller | 66178935 | Patricia White | 14740436 | Brian Taylor |  | Daniel Wright | 58116670 | Joshua Fischer | 32815223 | N/A | N/A | Pass | Fail | Pass | Andrew Rodriguez | 44715663 | United States | CFTC |  |  |  | MRA | FALSE | TRUE | TRUE | Operating Committee |  |  | Financial Reporting Control, Automated Control | 2022-11-04 |  | 2022-12-20 |  |  | Status update as of 2025-09-06. Remediation activities progressing. | 2025-09-06 | Nancy Weber | 72244897 | N40213 | DevOps | 2210 | UBS Europe SE Frankfurt | CTRL-3303082117, CTRL-3615507143, CTRL-6756332150, CTRL-4888749350 |  | Anti-Money Laundering, Organizational Culture
ISSUE-7567496105 | Examination Finding - AML Control Weakness - Investment Bank | Regulatory | Regulatory examination identified deficiencies in Cyber and Information Security compliance that require immediate attention. | Organizational changes affecting ownership | Documentation gaps and missing evidence | Potential regulatory sanctions or fines | All Cyber and Information Security controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2025-07-02 | 2025-10-26 | 1 | 1 | 1 | 5 | 2024-12-10 | 2025-06-15 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Andrew Li | 99081734 | Thomas Martinez | 84939694 | Margaret Brown |  | Henry Wright | 76549837 | Henry Jones | 75987872 | Fail | Pass | Fail | Fail | Pass | Joshua Moore | 83886264 | Singapore | MAS |  |  |  | MRIA | TRUE | TRUE | FALSE | Executive Committee | Business priority assessment completed. |  | Application Control, Financial Reporting Control | 2024-12-10 |  | 2025-01-16 |  |  | Status update as of 2025-06-15. Remediation activities progressing. | 2025-06-15 | Susan Johnson | 23776553 | N40113, N10112 | Control Testing, Electronic Trading | 2100, 4200, 4300 | UBS AG London Branch, UBS AG Singapore Branch, UBS Securities Japan Co Ltd | CTRL-5951406973, CTRL-2320763135, CTRL-7665963761 |  | Cyber and Information Security, Data Management
ISSUE-4289233844 | Regulatory Observation - Governance Deficiency - Group Functions | Regulatory | Regulatory examination identified deficiencies in Legal Risk compliance that require immediate attention. | Legacy systems limitations | Control exceptions not properly escalated | Reputational damage to the firm | All Legal Risk controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2023-05-18 | 2023-05-18 | 0 | 1 | 5 | 4 | 2022-05-22 | 2024-10-29 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Joshua White | 34901990 | Emma Kumar | 93241474 |  | 98354109 | Kevin White | 35483846 | [7 empty] | Jessica Lopez | 84016756 | Hong Kong | SFC |  |  |  |  | FALSE | FALSE | FALSE | Operating Committee |  |  | Key Control | 2022-05-22 |  | 2022-08-13 | 2024-05-12 |  | Status update as of 2024-10-29. Remediation activities progressing. | 2024-10-29 | Amelia Williams | 37122588 | N40213 | DevOps | 2210 | UBS Europe SE Frankfurt | CTRL-5067116918 |  | Legal Risk, Anti-Money Laundering
ISSUE-6633778586 | Regulatory Observation - Governance Deficiency - Asset Management | Regulatory | Regulatory examination identified deficiencies in Client Suitability compliance that require immediate attention. | Legacy systems limitations | Documentation gaps and missing evidence | Financial losses from operational errors | All Client Suitability controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2025-05-30 | 2025-06-29 | 1 | 0 | 5 | 3 | 2024-07-15 | 2024-02-05 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Jennifer Smith | 50310141 | Daniel Thomas | 52265790 |  | 47038339 | Karen Martinez | 22655004 | Oliver King | 57735307 | Pass | Pass | Fail | Fail | N/A | Evelyn Moore | 44392465 | United States | OCC |  |  |  | MRA | FALSE | TRUE | TRUE | Operating Committee |  |  | Automated Control, SOX Control, Regulatory Control | 2024-07-15 |  | 2024-08-16 | 2025-08-13 | 2025-01-25 | Status update as of 2024-02-05. Remediation activities progressing. | 2024-02-05 | Isabella Brown | 54881018 | N40113, N40413 | Control Testing, Capital Calculations | 3100 | UBS Securities LLC | CTRL-1965067727 | ISSUE-2812140441, ISSUE-3392080953 | Client Suitability
ISSUE-9894264595 | Regulatory Finding - Capital Calculation Error - Asset Management | Regulatory | Regulatory examination identified deficiencies in Client Suitability compliance that require immediate attention. | Inadequate process documentation and procedures | Delayed or incomplete reporting | Client complaints and relationship impact | All Client Suitability controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2023-04-16 | 2023-04-16 | 0 | 0 | 2 | 4 | 2022-10-12 | 2025-01-03 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Lucas Rodriguez | 11557295 | William Johnson | 29326800 | Susan Thompson | 28223512 | Isabella Rodriguez | 96200382 | Christopher King | 91125155 | Fail | N/A | Pass | Fail | N/A | Linda Young | 61635535 | Singapore | MAS |  |  |  | MRA | TRUE | FALSE | TRUE | Executive Committee | Business priority assessment completed. |  | Regulatory Control, IT General Control, Financial Reporting Control | 2022-10-12 |  | 2022-11-13 | 2024-02-08 | 2025-08-04 | Status update as of 2025-01-03. Remediation activities progressing. | 2025-01-03 | Andrew Kumar | 25188664 | N40213, N10122, N14963 | DevOps, Options Trading, Deal Execution | 3200, 3100, 4300 | UBS Financial Services Inc, UBS Securities LLC, UBS Securities Japan Co Ltd | CTRL-4274958945 | ISSUE-5728765136 | Client Suitability, Regulatory Compliance
ISSUE-3030106617 | Regulatory Examination Finding - Compliance Gap - Investment Bank | Regulatory | Regulatory examination identified deficiencies in Process Execution compliance that require immediate attention. | Insufficient training and awareness among staff | Increased error rates in processing | Client complaints and relationship impact | All Process Execution controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2023-07-13 | 2023-07-13 | 0 | 1 | 3 | 3 | 2022-07-20 | 2025-04-01 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Isabella Brown | 89743930 | Harper Davis | 26103055 |  | 60460287 | Brian Anderson | 24877375 | [7 empty] | Amelia Mueller | 49536330 | Hong Kong | HKMA |  |  |  |  | TRUE | FALSE | FALSE | Executive Committee |  |  | Regulatory Control, CCAR Control | 2022-07-20 |  | 2022-10-07 |  |  | Status update as of 2025-04-01. Remediation activities progressing. | 2025-04-01 | William Schmidt | 18373492 | N40113, N30113 | Control Testing, Portfolio Management | 3200 | UBS Financial Services Inc | CTRL-4466589567, CTRL-7567496105, CTRL-1939042955 |  | Process Execution
ISSUE-8763140509 | Regulatory Issue - Reporting Deficiency - Asset Management | Regulatory | Regulatory examination identified deficiencies in Sanctions Compliance compliance that require immediate attention. | Inadequate process documentation and procedures | Control exceptions not properly escalated | Potential regulatory sanctions or fines | All Sanctions Compliance controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2024-08-31 | 2024-08-31 | 0 | 0 | 3 | 4 | 2024-02-26 | 2025-02-03 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Matthew Taylor | 28782825 | Oliver Taylor | 13404379 | Nancy Jackson |  | William Fischer | 77066471 | [7 empty] | Kevin Young | 12203625 | Germany | BaFin |  |  |  | MRIA | TRUE | FALSE | TRUE | Executive Committee |  |  | Manual Control, Application Control, CCAR Control | 2024-02-26 |  | 2024-05-13 | 2025-08-16 | 2024-08-26 | Status update as of 2025-02-03. Remediation activities progressing. | 2025-02-03 | William Williams | 29003951 | N10112, N40213 | Electronic Trading, DevOps | 2100, 2210, 4100 | UBS AG London Branch, UBS Europe SE Frankfurt, UBS AG Hong Kong Branch | CTRL-9697354961, CTRL-4466589567 |  | Sanctions Compliance, Organizational Culture
ISSUE-1817804383 | Regulatory Observation - Governance Deficiency - Global Wealth Management | Regulatory | Regulatory examination identified deficiencies in Talent and Resource Management compliance that require immediate attention. | Legacy systems limitations | Increased error rates in processing | Potential regulatory sanctions or fines | All Talent and Resource Management controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2023-08-01 | 2023-08-01 | 0 | 3 | 4 | 5 | 2022-08-22 | 2025-09-22 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20200 | High Net Worth | N20210 | Wealth Planning | N20211 | Tax Advisory | N20212 | Estate Planning | N20213 | Trust Services | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Robert Davis | 87304983 | Kevin Rodriguez | 53163063 | Harper Williams | 55030548 | William Davis | 46761344 | Charlotte Martin | 32555403 | N/A | Fail | N/A | Pass | Fail | Evelyn Williams | 27900736 | Germany | BaFin |  |  |  |  | FALSE | TRUE | TRUE | Executive Committee |  |  | Automated Control | 2022-08-22 |  | 2022-11-16 |  |  | Status update as of 2025-09-22. Remediation activities progressing. | 2025-09-22 | David Martin | 73889312 | N14963, N20113, N40413 | Deal Execution, Investment Advisory, Capital Calculations | 3200, 4300, 3100 | UBS Financial Services Inc, UBS Securities Japan Co Ltd, UBS Securities LLC | CTRL-9786748825, CTRL-4466589567, CTRL-8086172302, CTRL-8987073217 |  | Talent and Resource Management, Outsourcing Risk
ISSUE-4590711152 | Examination Finding - AML Control Weakness - Asset Management | Regulatory | Regulatory examination identified deficiencies in Organizational Culture compliance that require immediate attention. | Resource constraints and competing priorities | Increased error rates in processing | Client complaints and relationship impact | All Organizational Culture controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-09-05 | 2024-09-05 | 0 | 0 | 2 | 5 | 2023-12-08 | 2024-02-27 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Isabella Jones | 50924657 | Mia Wang | 32787384 |  |  | Barbara Thompson | 86242300 | Joshua Martin | 45784981 | Pass | N/A | Fail | N/A | Pass | Robert White | 86551556 | Hong Kong | HKMA |  |  |  | MRIA | TRUE | FALSE | TRUE | Audit Committee |  |  | Financial Reporting Control, CCAR Control, Regulatory Control | 2023-12-08 |  | 2024-01-30 | 2025-03-22 |  | Status update as of 2024-02-27. Remediation activities progressing. | 2024-02-27 | Alexander Lopez | 95287876 | N40313 | Transaction Monitoring | 3200 | UBS Financial Services Inc | CTRL-2812140441, CTRL-6924716023, CTRL-5067116918 |  | Organizational Culture
ISSUE-9526836552 | Examination Issue - Risk Management Gap - Group Functions | Regulatory | Regulatory examination identified deficiencies in Technology Production Stability compliance that require immediate attention. | Organizational changes affecting ownership | Increased error rates in processing | Client complaints and relationship impact | All Technology Production Stability controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-06-28 | 2024-09-05 | 1 | 4 | 4 | 5 | 2024-02-05 | 2024-01-30 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Edward Smith | 54214932 | Oliver Young | 53609415 | Brian Rodriguez |  | Sophia Weber | 53375256 | Sophia Jones | 83438064 | N/A | Fail | Pass | Fail | Fail | Amelia Jackson | 63541768 | Germany | BaFin |  |  |  | MRA | TRUE | TRUE | FALSE | Executive Committee |  |  | CCAR Control, SOX Control, Regulatory Control | 2024-02-05 |  | 2024-04-06 |  |  | Status update as of 2024-01-30. Remediation activities progressing. | 2024-01-30 | Linda Fischer | 91002225 | N30113 | Portfolio Management | 2210, 4200, 1000 | UBS Europe SE Frankfurt, UBS AG Singapore Branch, UBS AG Zurich | CTRL-2948728483, CTRL-9639245200 | ISSUE-6884882440, ISSUE-1248786714 | Technology Production Stability, Sanctions Compliance
ISSUE-8380507338 | Examination Issue - Risk Management Gap - Investment Bank | Regulatory | Regulatory examination identified deficiencies in Data Management compliance that require immediate attention. | Legacy systems limitations | Documentation gaps and missing evidence | Potential regulatory sanctions or fines | All Data Management controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2025-06-05 | 2025-06-05 | 0 | 4 | 4 | 5 | 2024-06-07 | 2025-02-08 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Edward Lopez | 50641125 | Margaret Kumar | 63015631 | Isabella Rodriguez |  | Alexander Davis | 12132081 | Alexander Johnson | 38082305 | Fail | N/A | Pass | N/A | Pass | Linda Taylor | 21555280 | United States | OCC |  |  |  | MRIA | TRUE | FALSE | FALSE | Risk Committee |  | 2025-12-20 | Application Control, Automated Control | 2024-06-07 |  | 2024-07-08 |  |  | Status update as of 2025-02-08. Remediation activities progressing. | 2025-02-08 | Matthew Jackson | 37023185 | N40413, N40113 | Capital Calculations, Control Testing | 4100 | UBS AG Hong Kong Branch | CTRL-4460967357 |  | Data Management
ISSUE-7803990970 | Regulatory Matter - Customer Protection Issue - Investment Bank | Regulatory | Regulatory examination identified deficiencies in Conduct Risk compliance that require immediate attention. | Inadequate process documentation and procedures | Inconsistent application of procedures | Potential regulatory sanctions or fines | All Conduct Risk controls operating effectively with documented evidence and no exceptions. | Open | Red | Issue Mitigation Date at significant risk. Key dependencies delayed and remediation plan requires revision. | 2025-08-26 | 2025-08-26 | 0 | 2 | 2 | 3 | 2024-12-17 | 2024-04-03 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10110 | Cash Equities | N10111 | Execution Services | N10112 | Electronic Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Isabella Martinez | 51177222 | Christopher Wilson | 17907267 | Robert Anderson |  | Sophia Fischer | 62336822 | [7 empty] | Benjamin Chen | 29120731 | Japan | JFSA |  |  |  | MRIA | FALSE | FALSE | TRUE | Risk Committee |  |  | BCBS239 Control, Application Control, IT General Control | 2024-12-17 |  | 2025-03-17 |  |  | Status update as of 2024-04-03. Remediation activities progressing. | 2024-04-03 | Mia Schmidt | 18137886 | N40213, N40313 | DevOps, Transaction Monitoring | 2210, 3100 | UBS Europe SE Frankfurt, UBS Securities LLC | CTRL-1470939445 |  | Conduct Risk
ISSUE-6305160342 | Regulatory Finding - Capital Calculation Error - Global Wealth Management | Regulatory | Regulatory examination identified deficiencies in Conduct Risk compliance that require immediate attention. | Inadequate process documentation and procedures | Increased error rates in processing | Increased scrutiny from regulators | All Conduct Risk controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-11-02 | 2024-11-02 | 0 | 1 | 1 | 4 | 2024-06-17 | 2025-08-15 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20100 | Ultra High Net Worth | N20110 | Private Banking | N20111 | Client Advisory | N20112 | Portfolio Management | N20113 | Investment Advisory | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | William Rodriguez | 18321798 | Matthew Brown | 50462762 | Linda Jones |  | Sophia Brown | 49583058 | Thomas Harris | 22862118 | N/A | Fail | Pass | N/A | N/A | Margaret Smith | 70855827 | Hong Kong | HKMA |  |  |  | MRIA | FALSE | TRUE | FALSE | Risk Committee |  |  | SOX Control | 2024-06-17 |  | 2024-07-23 |  |  | Status update as of 2025-08-15. Remediation activities progressing. | 2025-08-15 | James Jones | 89575878 | N40413 | Capital Calculations | 3200 | UBS Financial Services Inc | CTRL-3694860228, CTRL-2867302554, CTRL-3030106617 |  | Conduct Risk
ISSUE-5278201677 | Regulatory Issue - Reporting Deficiency - Group Functions | Regulatory | Regulatory examination identified deficiencies in Cyber and Information Security compliance that require immediate attention. | Lack of automated controls and manual workarounds | Inconsistent application of procedures | Financial losses from operational errors | All Cyber and Information Security controls operating effectively with documented evidence and no exceptions. | Draft | Green | Remediation on track. All action plans progressing as planned. | 2023-08-04 | 2023-08-04 | 0 | 4 | 5 | 5 | 2023-02-18 | 2025-10-19 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Lucas Schmidt | 52619317 | Oliver Martin | 96979318 | Emma Moore | 54462343 | Elizabeth Jackson | 37624348 | Kevin Brown | 99255596 | Pass | N/A | N/A | N/A | Pass | Edward White | 79990777 | United States | OCC |  |  |  | MRA | FALSE | TRUE | TRUE | Executive Committee |  |  | CCAR Control, BCBS239 Control, Automated Control | 2023-02-18 |  |  |  |  | Status update as of 2025-10-19. Remediation activities progressing. | 2025-10-19 | Isabella Anderson | 89541539 | N20113, N40413, N10122 | Investment Advisory, Capital Calculations, Options Trading | 4300, 1000 | UBS Securities Japan Co Ltd, UBS AG Zurich | CTRL-3030106617, CTRL-2625792787 |  | Cyber and Information Security
ISSUE-9904586976 | Regulatory Matter - Customer Protection Issue - Investment Bank | Regulatory | Regulatory examination identified deficiencies in Sanctions Compliance compliance that require immediate attention. | Organizational changes affecting ownership | Delayed or incomplete reporting | Financial losses from operational errors | All Sanctions Compliance controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2025-01-20 | 2025-05-22 | 1 | 4 | 4 | 3 | 2024-09-12 | 2025-02-11 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Andrew Johnson | 61193233 | Linda Garcia | 50296396 | Charlotte Anderson |  | Barbara Fischer | 70881578 | David White | 85449435 | N/A | Fail | Pass | Fail | Pass | Andrew Taylor | 30766764 | United States | FINRA |  |  |  | MRA | TRUE | FALSE | FALSE | Executive Committee | Business priority assessment completed. | 2025-01-17 | Application Control, Regulatory Control | 2024-09-12 |  | 2024-11-22 |  |  | Status update as of 2025-02-11. Remediation activities progressing. | 2025-02-11 | Nancy Jones | 64866540 | N10122 | Options Trading | 1000, 2210 | UBS AG Zurich, UBS Europe SE Frankfurt | CTRL-6488854841, CTRL-4131356954, CTRL-7146318035, CTRL-3030106617 |  | Sanctions Compliance, Operational Resilience
ISSUE-9623534576 | Examination Finding - AML Control Weakness - Global Wealth Management | Regulatory | Regulatory examination identified deficiencies in Operational Resilience compliance that require immediate attention. | Lack of automated controls and manual workarounds | Delayed or incomplete reporting | Increased scrutiny from regulators | All Operational Resilience controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-09-19 | 2024-09-19 | 0 | 4 | 4 | 3 | 2024-05-14 | 2024-09-23 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20100 | Ultra High Net Worth | N20110 | Private Banking | N20111 | Client Advisory | N20112 | Portfolio Management | N20113 | Investment Advisory | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Linda Martinez | 81927860 | Harper Jones | 94499213 | Alexander Kumar | 96942366 | Joshua Wilson | 66329364 | Charlotte Chen | 68200448 | Fail | Pass | N/A | Pass | Pass | Sarah Davis | 81332718 | Switzerland | FINMA |  |  |  |  | FALSE | TRUE | FALSE | Risk Committee |  |  | CCAR Control, BCBS239 Control | 2024-05-14 |  | 2024-06-30 |  |  | Status update as of 2024-09-23. Remediation activities progressing. | 2024-09-23 | James Miller | 60621018 | N40113 | Control Testing | 2210 | UBS Europe SE Frankfurt | CTRL-9592390865, CTRL-8664882079 | ISSUE-3303082117, ISSUE-2699887270 | Operational Resilience