## Sheet1
issue_id | issue_title | issue_type | control_deficiency | root_cause | symptoms | risk_description | success_criteria | issue_status | issue_rag_status | issue_rag_justification | original_mitigation_date | current_mitigation_date | mitigation_date_change_count | open_action_plans | total_action_plans | severity_rating | created_on | last_modified_on | group_id | group_name | division_id | division_name | unit_id | unit_name | area_id | area_name | sector_id | sector_name | segment_id | segment_name | function_id | function_name | l0_location_id | l0_location_name | region_id | region_name | sub_region_id | sub_region_name | country_id | country_name | company_id | company_short_name | issue_owner | issue_owner_gpn | issue_administrator | issue_administrator_gpn | issue_delegate | issue_delegate_gpn | first_level_reviewer | first_level_reviewer_gpn | orc_reviewer | orc_reviewer_gpn | orc_articulation_check | orc_rating_check | orc_mitigation_date_check | orc_action_plan_check | orc_mapping_check | regulatory_manager | regulatory_manager_gpn | regulator_country | regulator_type | audit_rating | audit_report_id | finding_id | mra_mria | dsori_program | gsori_program | eandy_relevant | operating_committee | reprioritization_risk_acceptance_justification | risk_acceptance_approval_date | category_flags | draft_date | open_grace_period_date | open_date | completed_date | closed_date | last_comment | last_comment_date | last_commenter | last_commenter_gpn | related_function_ids | related_function_names | related_location_ids | related_location_names | linked_control_ids | related_issue_ids | risk_themes
ISSUE-7887950851 | Confidential Regulatory Issue - Enforcement Related - Group Functions | Restricted Regulatory | Confidential regulatory matter related to Anti-Money Laundering requiring restricted handling. | Organizational changes affecting ownership | Inconsistent application of procedures | Reputational damage to the firm | All Anti-Money Laundering controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2024-07-14 | 2024-07-14 | 0 | 0 | 4 | 3 | 2023-08-08 | 2024-05-18 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Matthew Garcia | 52894344 | John Jones | 83819367 | Jennifer Wilson | 95590648 | Amelia Kumar | 78284040 | Daniel Davis | 36975128 | Pass | Pass | Fail | Pass | Fail | Karen Kumar | 72734149 | Singapore | MAS |  |  |  |  | TRUE | TRUE | FALSE | Executive Committee | Business priority assessment completed. |  | IT General Control, Automated Control, SOX Control | 2023-08-08 |  | 2023-09-15 | 2024-11-20 | 2025-10-19 | Status update as of 2024-05-18. Remediation activities progressing. | 2024-05-18 | William Young | 72523073 | N40313, N30113, N14963 | Transaction Monitoring, Portfolio Management, Deal Execution | 1000, 4200, 2210 | UBS AG Zurich, UBS AG Singapore Branch, UBS Europe SE Frankfurt | CTRL-3615507143, CTRL-1127978094, CTRL-6756332150, CTRL-4274958945 |  | Anti-Money Laundering
ISSUE-4332894265 | Restricted Matter - Confidential Regulatory Issue - Investment Bank | Restricted Regulatory | Confidential regulatory matter related to Organizational Culture requiring restricted handling. | Legacy systems limitations | Increased error rates in processing | Financial losses from operational errors | All Organizational Culture controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-03-16 | 2024-03-16 | 0 | 2 | 2 | 3 | 2023-10-11 | 2025-08-05 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | William Smith | 45189912 | Harper Williams | 18115992 | Patricia Weber | 77249653 | Christopher Thompson | 63992760 | [7 empty] | Isabella Martinez | 47241089 | United States | SEC |  |  |  | MRIA | TRUE | TRUE | TRUE | Operating Committee |  |  | SOX Control, Regulatory Control, IT General Control | 2023-10-11 |  | 2023-12-26 |  |  | Status update as of 2025-08-05. Remediation activities progressing. | 2025-08-05 | Evelyn Brown | 42813517 | N40113 | Control Testing | 4300 | UBS Securities Japan Co Ltd | CTRL-3392080953 |  | Organizational Culture, Talent and Resource Management
ISSUE-5567816720 | Restricted Matter - Non-Public Examination Finding - Asset Management | Restricted Regulatory | Confidential regulatory matter related to Conduct Risk requiring restricted handling. | Lack of automated controls and manual workarounds | Delayed or incomplete reporting | Reputational damage to the firm | All Conduct Risk controls operating effectively with documented evidence and no exceptions. | Open | Red | Issue Mitigation Date at significant risk. Key dependencies delayed and remediation plan requires revision. | 2024-07-14 | 2024-07-14 | 0 | 2 | 5 | 3 | 2024-04-06 | 2024-05-14 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Oliver White | 95942441 | Michael Brown | 89715138 | Benjamin Johnson |  | Mia Martin | 69634854 | Thomas Davis | 83454998 | Fail | Fail | N/A | Pass | Pass | James Fischer | 66488410 | Singapore | MAS |  |  |  |  | FALSE | TRUE | FALSE | Risk Committee |  |  | SOX Control, Automated Control | 2024-04-06 |  | 2024-06-06 |  |  | Status update as of 2024-05-14. Remediation activities progressing. | 2024-05-14 | Alexander Taylor | 45298445 | N20113, N30113, N40113 | Investment Advisory, Portfolio Management, Control Testing | 1000, 2100 | UBS AG Zurich, UBS AG London Branch | CTRL-7665963761, CTRL-8987073217, CTRL-2867302554, CTRL-6649827836 |  | Conduct Risk
ISSUE-8168204967 | Restricted Finding - Sensitive Compliance Matter - Group Functions | Restricted Regulatory | Confidential regulatory matter related to Data Management requiring restricted handling. | Resource constraints and competing priorities | Inconsistent application of procedures | Client complaints and relationship impact | All Data Management controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-03-13 | 2024-05-24 | 1 | 1 | 1 | 3 | 2023-05-03 | 2024-08-03 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SB | UK & Ireland | C782 | United Kingdom | 2100 | UBS AG London Branch | Barbara Harris | 73918769 | Jennifer Wright | 81473736 |  | 62354374 | Andrew Mueller | 29481680 | [7 empty] | Jessica Thompson | 11592230 | United Kingdom | PRA |  |  |  | MRIA | FALSE | FALSE | TRUE | Risk Committee | Business priority assessment completed. |  | Automated Control, Regulatory Control | 2023-05-03 |  | 2023-06-23 |  |  | Status update as of 2024-08-03. Remediation activities progressing. | 2024-08-03 | Sarah Schmidt | 23190487 | N40413, N40113 | Capital Calculations, Control Testing | 3100, 4100 | UBS Securities LLC, UBS AG Hong Kong Branch | CTRL-4274958945, CTRL-2149938334 |  | Data Management, Third Party Management
ISSUE-7114223633 | Restricted Finding - Sensitive Compliance Matter - Investment Bank | Restricted Regulatory | Confidential regulatory matter related to Cyber and Information Security requiring restricted handling. | Inadequate process documentation and procedures | Control exceptions not properly escalated | Client complaints and relationship impact | All Cyber and Information Security controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2023-10-15 | 2023-10-15 | 0 | 1 | 3 | 3 | 2022-12-31 | 2025-04-13 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Oliver Brown | 47662052 | Lucas Davis | 72482955 |  |  | Elizabeth Moore | 49615907 | Edward Wilson | 95630804 | N/A | Pass | N/A | N/A | Pass | Isabella Martin | 80030620 | Japan | JFSA |  |  |  | MRA | FALSE | FALSE | FALSE | Risk Committee |  |  | BCBS239 Control | 2022-12-31 |  | 2023-02-19 | 2025-03-20 |  | Status update as of 2025-04-13. Remediation activities progressing. | 2025-04-13 | Nancy Moore | 89426243 | N40413 | Capital Calculations | 4200 | UBS AG Singapore Branch | CTRL-9963334018 | ISSUE-5567816720 | Cyber and Information Security, Regulatory Compliance
ISSUE-2811967841 | Restricted Matter - Non-Public Examination Finding - Group Functions | Restricted Regulatory | Confidential regulatory matter related to Organizational Culture requiring restricted handling. | Organizational changes affecting ownership | Increased error rates in processing | Financial losses from operational errors | All Organizational Culture controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2025-02-21 | 2025-05-03 | 1 | 2 | 2 | 3 | 2024-11-15 | 2025-08-18 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40400 | Group Finance | N40410 | Financial Reporting | N40411 | Regulatory Reporting | N40412 | Capital Reporting | N40413 | Capital Calculations | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Maria Martin | 95395644 | John Brown | 48903840 |  | 20311502 | Joshua Taylor | 94292753 | [7 empty] | Amelia Miller | 90364540 | Singapore | MAS |  |  |  |  | FALSE | FALSE | FALSE | Operating Committee |  |  | Manual Control | 2024-11-15 |  | 2025-01-21 |  |  | Status update as of 2025-08-18. Remediation activities progressing. | 2025-08-18 | John Martinez | 11731095 | N40313 | Transaction Monitoring | 4100, 4200 | UBS AG Hong Kong Branch, UBS AG Singapore Branch | CTRL-1470939445, CTRL-2149938334, CTRL-8934927891, CTRL-4460967357 |  | Organizational Culture, Process Execution
ISSUE-1251837136 | Restricted Matter - Non-Public Examination Finding - Global Wealth Management | Restricted Regulatory | Confidential regulatory matter related to Client Suitability requiring restricted handling. | Inadequate process documentation and procedures | Control exceptions not properly escalated | Reputational damage to the firm | All Client Suitability controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-02-05 | 2024-02-05 | 0 | 1 | 1 | 4 | 2023-08-03 | 2025-02-22 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20200 | High Net Worth | N20210 | Wealth Planning | N20211 | Tax Advisory | N20212 | Estate Planning | N20213 | Trust Services | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3200 | UBS Financial Services Inc | Matthew Jackson | 59611937 | Nancy King | 21507650 |  |  | Robert Harris | 38483372 | [7 empty] | Thomas Thompson | 90154282 | United States | OCC |  |  |  | MRA | TRUE | TRUE | TRUE | Operating Committee | Business priority assessment completed. |  | Automated Control, Key Control | 2023-08-03 |  | 2023-09-02 | 2024-09-16 |  | Status update as of 2025-02-22. Remediation activities progressing. | 2025-02-22 | Joshua White | 50601849 | N30113, N14963 | Portfolio Management, Deal Execution | 2100, 3200, 2210 | UBS AG London Branch, UBS Financial Services Inc, UBS Europe SE Frankfurt | CTRL-7887950851, CTRL-3615507143, CTRL-4919706735 | ISSUE-1667779376, ISSUE-6241752544 | Client Suitability, Third Party Management