## Self_Identified
Timestamp: 2026-01-25 15:12:47
issue_id | issue_title | issue_type | control_deficiency | root_cause | symptoms | risk_description | success_criteria | issue_status | issue_rag_status | issue_rag_justification | original_mitigation_date | current_mitigation_date | mitigation_date_change_count | open_action_plans | total_action_plans | severity_rating | created_on | last_modified_on | group_id | group_name | division_id | division_name | unit_id | unit_name | area_id | area_name | sector_id | sector_name | segment_id | segment_name | function_id | function_name | l0_location_id | l0_location_name | region_id | region_name | sub_region_id | sub_region_name | country_id | country_name | company_id | company_short_name | issue_owner | issue_owner_gpn | issue_administrator | issue_administrator_gpn | issue_delegate | issue_delegate_gpn | first_level_reviewer | first_level_reviewer_gpn | orc_reviewer | orc_reviewer_gpn | orc_articulation_check | orc_rating_check | orc_mitigation_date_check | orc_action_plan_check | orc_mapping_check | regulatory_manager | regulatory_manager_gpn | regulator_country | regulator_type | audit_rating | audit_report_id | finding_id | mra_mria | dsori_program | gsori_program | eandy_relevant | operating_committee | reprioritization_risk_acceptance_justification | risk_acceptance_approval_date | category_flags | draft_date | open_grace_period_date | open_date | completed_date | closed_date | last_comment | last_comment_date | last_commenter | last_commenter_gpn | related_function_ids | related_function_names | related_location_ids | related_location_names | linked_control_ids | related_issue_ids | risk_themes
ISSUE-9963334018 | Self-Assessment Finding - Documentation Deficiency - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Operational Resilience processes that require remediation. | Insufficient training and awareness among staff | Delayed or incomplete reporting | Potential regulatory sanctions or fines | All Operational Resilience controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2024-11-23 | 2025-03-30 | 1 | 0 | 3 | 5 | 2024-05-02 | 2025-04-06 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10110 | Cash Equities | N10111 | Execution Services | N10112 | Electronic Trading | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Jennifer Brown | 91823275 | Benjamin Thomas | 93955206 |  | 31079846 | Evelyn Anderson | 84087145 | William Wilson | 10359129 | Fail | Fail | N/A | N/A | Fail | [8 empty] | FALSE | TRUE | TRUE | Operating Committee |  |  | SOX Control, BCBS239 Control | 2024-05-02 | 2024-06-01 | 2024-06-17 | 2025-10-02 | 2025-08-26 | Status update as of 2025-04-06. Remediation activities progressing. | 2025-04-06 | Alexander Thompson | 25405014 | N20113, N14963, N20213 | Investment Advisory, Deal Execution, Trust Services | 2210 | UBS Europe SE Frankfurt | CTRL-7887950851 | ISSUE-1958682846, ISSUE-3746317213 | Operational Resilience
ISSUE-2812140441 | Management Review Finding - Training Gap - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Legal Risk processes that require remediation. | Insufficient training and awareness among staff | Inconsistent application of procedures | Financial losses from operational errors | All Legal Risk controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2023-09-08 | 2023-09-08 | 0 | 0 | 5 | 5 | 2023-05-28 | 2025-11-21 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3200 | UBS Financial Services Inc | Brian Williams | 33513701 | Andrew Young | 47333543 |  | 95199362 | Susan Garcia | 73083727 | John Martin | 54735895 | Fail | N/A | Pass | Pass | Fail | [8 empty] | FALSE | FALSE | FALSE | Executive Committee | Business priority assessment completed. |  | SOX Control, Financial Reporting Control | 2023-05-28 | 2023-06-06 | 2023-07-17 | 2024-04-28 |  | Status update as of 2025-11-21. Remediation activities progressing. | 2025-11-21 | Patricia Smith | 98269682 | N40213, N40113, N10112 | DevOps, Control Testing, Electronic Trading | 4100 | UBS AG Hong Kong Branch | CTRL-1519709079, CTRL-7567496105, CTRL-7114223633, CTRL-2812140441 |  | Legal Risk, Data Management
ISSUE-1939042955 | Self-Identified - System Configuration Error - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Business Continuity processes that require remediation. | Insufficient training and awareness among staff | Delayed or incomplete reporting | Client complaints and relationship impact | All Business Continuity controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2023-03-21 | 2023-03-21 | 0 | 1 | 1 | 5 | 2022-11-13 | 2024-09-28 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Thomas Chen | 94127561 | Susan Williams | 92874006 |  | 48571356 | Daniel Garcia | 68246664 | Benjamin Miller | 69549527 | Pass | N/A | Fail | Pass | Pass | [8 empty] | FALSE | TRUE | FALSE | Operating Committee |  |  | IT General Control, CCAR Control, Manual Control | 2022-11-13 | 2022-11-19 | 2022-12-18 |  |  | Status update as of 2024-09-28. Remediation activities progressing. | 2024-09-28 | Margaret White | 93176117 | N20113, N40213, N14963 | Investment Advisory, DevOps, Deal Execution | 4300 | UBS Securities Japan Co Ltd | CTRL-4095476665, CTRL-6488854841, CTRL-3710566582 |  | Business Continuity
ISSUE-7635473142 | Self-Identified Issue - Process Execution Gap - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Physical Security processes that require remediation. | Resource constraints and competing priorities | Increased error rates in processing | Financial losses from operational errors | All Physical Security controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2023-07-30 | 2023-07-30 | 0 | 1 | 3 | 5 | 2022-09-11 | 2025-11-19 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Emma Chen | 91883846 | Daniel Jones | 95282470 | Jennifer Martin |  | Oliver Williams | 50851122 | [15 empty] | FALSE | TRUE | TRUE | Audit Committee | Business priority assessment completed. |  | Financial Reporting Control, Manual Control | 2022-09-11 | 2022-09-25 | 2022-11-17 |  |  | Status update as of 2025-11-19. Remediation activities progressing. | 2025-11-19 | Charlotte Martin | 97902129 | N40213 | DevOps | 4200, 1000, 2100 | UBS AG Singapore Branch, UBS AG Zurich, UBS AG London Branch | CTRL-8995970241, CTRL-7567496105, CTRL-9786748825 | ISSUE-9963334018 | Physical Security, Market Conduct
ISSUE-6241752544 | Control Self-Assessment - Evidence Retention Issue - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Intragroup Dependencies processes that require remediation. | Resource constraints and competing priorities | Increased error rates in processing | Reputational damage to the firm | All Intragroup Dependencies controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2022-06-08 | 2022-09-08 | 1 | 0 | 2 | 5 | 2022-02-13 | 2024-05-08 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10110 | Cash Equities | N10111 | Execution Services | N10112 | Electronic Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Harper Moore | 54098516 | Charlotte Smith | 47215199 | Charlotte Rodriguez | 33420607 | Mia Johnson | 27690330 | [15 empty] | TRUE | FALSE | TRUE | Operating Committee |  |  | IT General Control | 2022-02-13 | 2022-03-02 | 2022-03-22 | 2024-03-06 |  | Status update as of 2024-05-08. Remediation activities progressing. | 2024-05-08 | Andrew Young | 58592048 | N40413, N10122, N40213 | Capital Calculations, Options Trading, DevOps | 3100, 3200, 2100 | UBS Securities LLC, UBS Financial Services Inc, UBS AG London Branch | CTRL-4095476665, CTRL-2452066459, CTRL-1958682846 |  | Intragroup Dependencies, Technology Change Management
ISSUE-4460967357 | Self-Identified - System Configuration Error - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Process Execution processes that require remediation. | Inadequate process documentation and procedures | Increased error rates in processing | Financial losses from operational errors | All Process Execution controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-06-19 | 2024-12-12 | 1 | 0 | 5 | 5 | 2024-01-23 | 2024-08-19 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Sarah Johnson | 34215035 | Sarah Fischer | 55610493 |  |  | Charlotte Harris | 19339597 | Charlotte Johnson | 22315507 | N/A | N/A | Pass | Fail | Fail | [8 empty] | FALSE | FALSE | TRUE | Operating Committee |  |  | Automated Control, SOX Control, Key Control | 2024-01-23 | 2024-01-28 | 2024-03-03 | 2025-09-24 |  | Status update as of 2024-08-19. Remediation activities progressing. | 2024-08-19 | Sophia Garcia | 46521025 | N40113, N40213 | Control Testing, DevOps | 4300, 3100, 1000 | UBS Securities Japan Co Ltd, UBS Securities LLC, UBS AG Zurich | CTRL-7146318035, CTRL-5951406973 |  | Process Execution
ISSUE-6756332150 | Self-Identified Issue - Process Execution Gap - Asset Management | Self-Identified | Management self-assessment identified weaknesses in Financial Crime Prevention processes that require remediation. | Inadequate process documentation and procedures | Documentation gaps and missing evidence | Reputational damage to the firm | All Financial Crime Prevention controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2023-06-08 | 2023-07-27 | 1 | 0 | 4 | 4 | 2022-12-22 | 2024-06-30 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Nancy Young | 85764804 | Margaret Chen | 94183695 |  |  | Andrew Young | 94743076 | Jennifer Schmidt | 89379016 | Pass | Fail | N/A | Pass | Fail | [8 empty] | FALSE | FALSE | TRUE | Risk Committee |  |  | SOX Control, Manual Control, IT General Control | 2022-12-22 | 2023-01-06 | 2023-02-27 | 2025-07-21 | 2024-02-12 | Status update as of 2024-06-30. Remediation activities progressing. | 2024-06-30 | Matthew Taylor | 53154591 | N40213, N40313, N14963 | DevOps, Transaction Monitoring, Deal Execution | 4300 | UBS Securities Japan Co Ltd | CTRL-2149938334 | ISSUE-1939042955 | Financial Crime Prevention
ISSUE-1667779376 | Management Review Finding - Training Gap - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Legal Risk processes that require remediation. | Legacy systems limitations | Delayed or incomplete reporting | Financial losses from operational errors | All Legal Risk controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-09-24 | 2024-09-24 | 0 | 1 | 1 | 3 | 2024-02-03 | 2024-12-12 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10110 | Cash Equities | N10111 | Execution Services | N10112 | Electronic Trading | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Karen White | 48137561 | Michael Martinez | 54743095 |  | 56952151 | Jennifer Harris | 27307598 | Edward Garcia | 51551377 | N/A | Fail | N/A | Fail | Pass | [8 empty] | TRUE | FALSE | FALSE | Risk Committee |  |  | Financial Reporting Control | 2024-02-03 | 2024-02-28 | 2024-04-04 | 2024-07-15 |  | Status update as of 2024-12-12. Remediation activities progressing. | 2024-12-12 | Daniel Rodriguez | 30796389 | N20213 | Trust Services | 2100 | UBS AG London Branch | CTRL-4131356954, CTRL-7517938612, CTRL-1667779376 |  | Legal Risk, Business Continuity
ISSUE-5693307665 | Self-Identified Issue - Escalation Process Failure - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Transaction Processing processes that require remediation. | Lack of automated controls and manual workarounds | Delayed or incomplete reporting | Reputational damage to the firm | All Transaction Processing controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2022-11-11 | 2023-04-10 | 1 | 1 | 4 | 5 | 2022-03-20 | 2025-12-13 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10110 | Cash Equities | N10111 | Execution Services | N10112 | Electronic Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Isabella Johnson | 44349528 | Harper Martinez | 83659258 | Edward Thompson |  | David Jackson | 50419829 | [15 empty] | TRUE | TRUE | TRUE | Executive Committee |  |  | SOX Control | 2022-03-20 | 2022-04-16 | 2022-06-15 | 2025-05-26 |  | Status update as of 2025-12-13. Remediation activities progressing. | 2025-12-13 | Edward Johnson | 94819556 | N40413, N20113, N14963 | Capital Calculations, Investment Advisory, Deal Execution | 4200, 2100 | UBS AG Singapore Branch, UBS AG London Branch | CTRL-9786748825, CTRL-5067116918, CTRL-3694860228 |  | Transaction Processing
ISSUE-5710360983 | Management Review Finding - Training Gap - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Business Continuity processes that require remediation. | Legacy systems limitations | Control exceptions not properly escalated | Increased scrutiny from regulators | All Business Continuity controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2022-11-27 | 2023-01-07 | 1 | 1 | 1 | 3 | 2022-02-11 | 2025-10-12 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Benjamin Wang | 27905932 | Oliver Li | 83284724 |  | 72360629 | Andrew Anderson | 28099607 | William King | 14963880 | Fail | Pass | Pass | Pass | Pass | [8 empty] | FALSE | FALSE | FALSE | Executive Committee |  |  | Regulatory Control | 2022-02-11 | 2022-02-23 | 2022-05-07 |  |  | Status update as of 2025-10-12. Remediation activities progressing. | 2025-10-12 | Sophia Wang | 46670512 | N30113 | Portfolio Management | 4200, 4100 | UBS AG Singapore Branch, UBS AG Hong Kong Branch | CTRL-7010379415, CTRL-2149938334, CTRL-8429141456, CTRL-4919706735 |  | Business Continuity
ISSUE-8934927891 | Self-Identified Issue - Process Execution Gap - Asset Management | Self-Identified | Management self-assessment identified weaknesses in Regulatory Compliance processes that require remediation. | Resource constraints and competing priorities | Control exceptions not properly escalated | Reputational damage to the firm | All Regulatory Compliance controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-05-05 | 2024-05-05 | 0 | 1 | 3 | 5 | 2023-08-25 | 2024-12-01 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3200 | UBS Financial Services Inc | Henry Young | 57183837 | Matthew Williams | 57319709 | Linda Schmidt | 17698469 | William Harris | 58762794 | Joshua Wilson | 14179623 | Pass | N/A | N/A | Fail | Pass | [8 empty] | TRUE | TRUE | TRUE | Operating Committee |  | 2024-02-03 | CCAR Control, Application Control, Financial Reporting Control | 2023-08-25 | 2023-09-06 | 2023-10-22 | 2024-03-19 |  | Status update as of 2024-12-01. Remediation activities progressing. | 2024-12-01 | Brian Rodriguez | 81062902 | N40113, N30113 | Control Testing, Portfolio Management | 3200, 2210, 2100 | UBS Financial Services Inc, UBS Europe SE Frankfurt, UBS AG London Branch | CTRL-8763140509 |  | Regulatory Compliance
ISSUE-4466589567 | Self-Assessment Finding - Documentation Deficiency - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Transaction Processing processes that require remediation. | Legacy systems limitations | Documentation gaps and missing evidence | Potential regulatory sanctions or fines | All Transaction Processing controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2023-12-05 | 2023-12-05 | 0 | 5 | 5 | 3 | 2023-05-29 | 2025-07-18 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Henry Martinez | 32978158 | Margaret Wang | 85647532 |  | 20901547 | Oliver Mueller | 97393186 | Harper Martin | 92961108 | N/A | Pass | Fail | N/A | N/A | [8 empty] | FALSE | FALSE | FALSE | Audit Committee | Business priority assessment completed. |  | Application Control, SOX Control | 2023-05-29 | 2023-06-21 | 2023-07-01 |  |  | Status update as of 2025-07-18. Remediation activities progressing. | 2025-07-18 | Henry Young | 65783806 | N40213, N20113 | DevOps, Investment Advisory | 1000, 4300 | UBS AG Zurich, UBS Securities Japan Co Ltd | CTRL-8664882079, CTRL-2351531223, CTRL-7483366056 |  | Transaction Processing, Financial Crime Prevention
ISSUE-8995970241 | Self-Assessment Finding - Documentation Deficiency - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Anti-Money Laundering processes that require remediation. | Legacy systems limitations | Control exceptions not properly escalated | Potential regulatory sanctions or fines | All Anti-Money Laundering controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-03-20 | 2024-03-20 | 0 | 1 | 4 | 3 | 2023-06-20 | 2024-03-04 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Joshua Fischer | 25759274 | David Kumar | 92493631 |  | 74180488 | Charlotte King | 91300905 | Maria Martin | 83717007 | Fail | N/A | N/A | Pass | Pass | [8 empty] | TRUE | FALSE | FALSE | Risk Committee | Business priority assessment completed. |  | Manual Control, BCBS239 Control, CCAR Control | 2023-06-20 | 2023-06-26 | 2023-08-09 | 2025-06-16 |  | Status update as of 2024-03-04. Remediation activities progressing. | 2024-03-04 | Matthew Davis | 37568520 | N40413, N40213, N10122 | Capital Calculations, DevOps, Options Trading | 4300, 4200, 2100 | UBS Securities Japan Co Ltd, UBS AG Singapore Branch, UBS AG London Branch | CTRL-1667779376, CTRL-5951406973, CTRL-3694860228, CTRL-4095476665 |  | Anti-Money Laundering, Conduct Risk
ISSUE-5728765136 | Self-Identified Issue - Escalation Process Failure - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Physical Security processes that require remediation. | Lack of automated controls and manual workarounds | Documentation gaps and missing evidence | Client complaints and relationship impact | All Physical Security controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2025-08-22 | 2025-08-22 | 0 | 2 | 4 | 5 | 2024-10-01 | 2024-12-26 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40400 | Group Finance | N40410 | Financial Reporting | N40411 | Regulatory Reporting | N40412 | Capital Reporting | N40413 | Capital Calculations | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Sophia Williams | 19976458 | Sophia Smith | 65350347 |  | 19122502 | Charlotte Smith | 39356057 | Joshua King | 60090149 | Pass | N/A | N/A | N/A | N/A | [8 empty] | FALSE | FALSE | TRUE | Risk Committee |  |  | Manual Control | 2024-10-01 | 2024-10-25 | 2024-11-17 |  |  | Status update as of 2024-12-26. Remediation activities progressing. | 2024-12-26 | Kevin Weber | 12300840 | N40113, N14963, N10122 | Control Testing, Deal Execution, Options Trading | 1000 | UBS AG Zurich | CTRL-3303082117, CTRL-7517938612 |  | Physical Security, Organizational Culture
ISSUE-2566942273 | Self-Identified Issue - Escalation Process Failure - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Conduct Risk processes that require remediation. | Lack of automated controls and manual workarounds | Inconsistent application of procedures | Client complaints and relationship impact | All Conduct Risk controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-01-10 | 2024-01-10 | 0 | 1 | 4 | 5 | 2023-04-13 | 2025-01-19 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Evelyn Jones | 21010955 | Sarah Martinez | 61002735 | Charlotte White |  | Benjamin Garcia | 10697290 | [15 empty] | FALSE | FALSE | FALSE | Operating Committee |  |  | Application Control, Manual Control | 2023-04-13 | 2023-05-01 | 2023-06-14 |  |  | Status update as of 2025-01-19. Remediation activities progressing. | 2025-01-19 | Christopher Miller | 13524813 | N30113 | Portfolio Management | 2210, 3200, 4200 | UBS Europe SE Frankfurt, UBS Financial Services Inc, UBS AG Singapore Branch | CTRL-7010379415, CTRL-9697354961, CTRL-5996775663 |  | Conduct Risk, Technology Production Stability
ISSUE-3783290795 | Control Self-Assessment - Evidence Retention Issue - Global Wealth Management | Self-Identified | Management self-assessment identified weaknesses in Transaction Processing processes that require remediation. | Resource constraints and competing priorities | Inconsistent application of procedures | Reputational damage to the firm | All Transaction Processing controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-04-13 | 2024-04-13 | 0 | 0 | 4 | 4 | 2023-09-13 | 2024-06-06 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20100 | Ultra High Net Worth | N20110 | Private Banking | N20111 | Client Advisory | N20112 | Portfolio Management | N20113 | Investment Advisory | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Andrew Harris | 81721578 | Joshua Martin | 82966824 |  | 82062301 | Edward Garcia | 24679315 | Evelyn Li | 32325574 | N/A | N/A | Pass | N/A | N/A | [8 empty] | FALSE | FALSE | FALSE | Risk Committee |  |  | Manual Control, Automated Control, BCBS239 Control | 2023-09-13 | 2023-09-28 | 2023-11-05 | 2025-02-04 |  | Status update as of 2024-06-06. Remediation activities progressing. | 2024-06-06 | Barbara Martinez | 56300738 | N40213 | DevOps | 3200 | UBS Financial Services Inc | CTRL-7635473142, CTRL-8293453178, CTRL-8664882079, CTRL-5693307665 |  | Transaction Processing, Data Management
ISSUE-4131575764 | Self-Identified - System Configuration Error - Asset Management | Self-Identified | Management self-assessment identified weaknesses in Business Continuity processes that require remediation. | Lack of automated controls and manual workarounds | Inconsistent application of procedures | Potential regulatory sanctions or fines | All Business Continuity controls operating effectively with documented evidence and no exceptions. | Draft | Green | Remediation on track. All action plans progressing as planned. | 2025-05-03 | 2025-05-03 | 0 | 1 | 1 | 5 | 2024-06-16 | 2024-11-03 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Henry Jackson | 79255529 | Amelia Wilson | 54424679 | Barbara Moore | 94524999 | Amelia Anderson | 95963619 | [15 empty] | FALSE | FALSE | TRUE | Audit Committee |  |  | BCBS239 Control | 2024-06-16 | 2024-06-23 |  |  |  | Status update as of 2024-11-03. Remediation activities progressing. | 2024-11-03 | Sarah Jones | 87490324 | N40313 | Transaction Monitoring | 4100 | UBS AG Hong Kong Branch | CTRL-2625792787, CTRL-4095476665, CTRL-8293453178 |  | Business Continuity
ISSUE-5996775663 | Management Review Finding - Training Gap - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Talent and Resource Management processes that require remediation. | Insufficient training and awareness among staff | Documentation gaps and missing evidence | Financial losses from operational errors | All Talent and Resource Management controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2025-01-20 | 2025-05-06 | 1 | 1 | 3 | 3 | 2024-07-26 | 2025-09-21 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Amelia Kumar | 28972822 | Joshua White | 66135102 | Brian White |  | Susan Anderson | 84479105 | Henry Lopez | 48766747 | Pass | Pass | Fail | Fail | N/A | [8 empty] | TRUE | FALSE | TRUE | Executive Committee |  |  | Manual Control, Application Control, IT General Control | 2024-07-26 | 2024-08-17 | 2024-09-25 |  |  | Status update as of 2025-09-21. Remediation activities progressing. | 2025-09-21 | Christopher Young | 75592138 | N10122 | Options Trading | 2100, 4200, 2210 | UBS AG London Branch, UBS AG Singapore Branch, UBS Europe SE Frankfurt | CTRL-4163119785, CTRL-3783290795, CTRL-3479708607 |  | Talent and Resource Management, Client Suitability
ISSUE-3392080953 | Self-Assessment Finding - Documentation Deficiency - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Legal Risk processes that require remediation. | Legacy systems limitations | Increased error rates in processing | Potential regulatory sanctions or fines | All Legal Risk controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2025-04-26 | 2025-10-09 | 1 | 2 | 2 | 4 | 2024-07-27 | 2025-02-11 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3200 | UBS Financial Services Inc | David Wang | 83458776 | Brian Rodriguez | 85986307 | Elizabeth Brown |  | Barbara Johnson | 26674831 | Henry Young | 71272827 | Pass | Fail | Pass | N/A | Pass | [8 empty] | FALSE | TRUE | FALSE | Risk Committee |  |  | CCAR Control, Key Control | 2024-07-27 | 2024-08-09 | 2024-10-05 |  |  | Status update as of 2025-02-11. Remediation activities progressing. | 2025-02-11 | Jennifer Moore | 67610401 | N10122, N40413, N10112 | Options Trading, Capital Calculations, Electronic Trading | 4300 | UBS Securities Japan Co Ltd | CTRL-1667779376 |  | Legal Risk, Regulatory Change
ISSUE-8235363119 | Self-Identified Issue - Escalation Process Failure - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Technology Production Stability processes that require remediation. | Lack of automated controls and manual workarounds | Increased error rates in processing | Client complaints and relationship impact | All Technology Production Stability controls operating effectively with documented evidence and no exceptions. | Open-Grace Period | Green | Remediation on track. All action plans progressing as planned. | 2023-08-28 | 2023-08-28 | 0 | 1 | 1 | 4 | 2022-09-28 | 2025-01-27 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Lucas White | 27870584 | Charlotte Jones | 81203615 | Margaret Wilson |  | Harper Martinez | 65258766 | Margaret Young | 39158087 | Pass | Pass | Pass | Pass | N/A | [8 empty] | FALSE | FALSE | FALSE | Operating Committee |  |  | SOX Control, BCBS239 Control, Regulatory Control | 2022-09-28 | 2022-10-23 | 2022-12-27 |  |  | Status update as of 2025-01-27. Remediation activities progressing. | 2025-01-27 | Emma Fischer | 37574457 | N40413, N40313, N20113 | Capital Calculations, Transaction Monitoring, Investment Advisory | 4200, 1000, 4100 | UBS AG Singapore Branch, UBS AG Zurich, UBS AG Hong Kong Branch | CTRL-9786748825 |  | Technology Production Stability
ISSUE-8110054933 | Management Review Finding - Training Gap - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Outsourcing Risk processes that require remediation. | Resource constraints and competing priorities | Inconsistent application of procedures | Client complaints and relationship impact | All Outsourcing Risk controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2022-12-12 | 2022-12-12 | 0 | 2 | 3 | 4 | 2022-03-02 | 2024-06-25 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10110 | Cash Equities | N10111 | Execution Services | N10112 | Electronic Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Oliver Jackson | 96876236 | David Lopez | 65296657 | Andrew Brown |  | Thomas Rodriguez | 66268745 | Alexander Jackson | 94658420 | N/A | Pass | Fail | N/A | Fail | [8 empty] | FALSE | FALSE | FALSE | Operating Committee |  |  | Automated Control, BCBS239 Control | 2022-03-02 | 2022-03-03 | 2022-05-28 |  |  | Status update as of 2024-06-25. Remediation activities progressing. | 2024-06-25 | Sarah Brown | 73308406 | N30113, N20113, N14963 | Portfolio Management, Investment Advisory, Deal Execution | 3100 | UBS Securities LLC | CTRL-6884882440, CTRL-6687206971 | ISSUE-8293453178 | Outsourcing Risk
ISSUE-7805745017 | Management Identified - Control Operating Effectiveness - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Conduct Risk processes that require remediation. | Inadequate process documentation and procedures | Inconsistent application of procedures | Increased scrutiny from regulators | All Conduct Risk controls operating effectively with documented evidence and no exceptions. | Draft | Green | Remediation on track. All action plans progressing as planned. | 2024-02-17 | 2024-02-17 | 0 | 2 | 4 | 3 | 2023-06-28 | 2024-04-08 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SB | UK & Ireland | C782 | United Kingdom | 2100 | UBS AG London Branch | Linda Garcia | 49533757 | Edward Wright | 36799898 |  |  | David Garcia | 73561576 | Mia Fischer | 63347164 | Fail | Fail | N/A | Fail | Pass | [8 empty] | FALSE | TRUE | FALSE | Executive Committee |  |  | Application Control, Automated Control | 2023-06-28 | 2023-07-07 |  |  |  | Status update as of 2024-04-08. Remediation activities progressing. | 2024-04-08 | Daniel Schmidt | 85731895 | N14963 | Deal Execution | 2210, 2100, 4100 | UBS Europe SE Frankfurt, UBS AG London Branch, UBS AG Hong Kong Branch | CTRL-1083651970, CTRL-1470939445, CTRL-7146318035 |  | Conduct Risk
ISSUE-9639245200 | Control Self-Assessment - Evidence Retention Issue - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Cyber and Information Security processes that require remediation. | Resource constraints and competing priorities | Documentation gaps and missing evidence | Increased scrutiny from regulators | All Cyber and Information Security controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2025-05-29 | 2025-07-27 | 1 | 0 | 2 | 4 | 2024-08-26 | 2024-04-09 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | David Kumar | 24270328 | Oliver Wilson | 76091781 |  | 64923338 | Benjamin Mueller | 91987136 | Alexander Taylor | 26206227 | Fail | Pass | Fail | Pass | N/A | [8 empty] | FALSE | TRUE | FALSE | Risk Committee | Business priority assessment completed. |  | SOX Control, Application Control, Manual Control | 2024-08-26 | 2024-09-17 | 2024-11-01 | 2025-05-31 |  | Status update as of 2024-04-09. Remediation activities progressing. | 2024-04-09 | Lucas Lopez | 10582186 | N10112, N40313, N40113 | Electronic Trading, Transaction Monitoring, Control Testing | 4300, 3200, 2210 | UBS Securities Japan Co Ltd, UBS Financial Services Inc, UBS Europe SE Frankfurt | CTRL-8664882079, CTRL-1667779376 |  | Cyber and Information Security, Financial Crime Prevention
ISSUE-4095476665 | Self-Identified Issue - Escalation Process Failure - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Regulatory Compliance processes that require remediation. | Inadequate process documentation and procedures | Documentation gaps and missing evidence | Client complaints and relationship impact | All Regulatory Compliance controls operating effectively with documented evidence and no exceptions. | Open-Grace Period | Green | Remediation on track. All action plans progressing as planned. | 2024-07-31 | 2024-07-31 | 0 | 3 | 5 | 5 | 2023-12-04 | 2024-05-16 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40400 | Group Finance | N40410 | Financial Reporting | N40411 | Regulatory Reporting | N40412 | Capital Reporting | N40413 | Capital Calculations | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Robert Thomas | 36962876 | Harper Weber | 56344519 | Lucas Anderson | 95480242 | Robert Davis | 57276557 | Karen Wright | 88222933 | N/A | N/A | N/A | Fail | N/A | [8 empty] | FALSE | FALSE | TRUE | Risk Committee |  |  | Key Control, BCBS239 Control, Regulatory Control | 2023-12-04 | 2023-12-29 | 2024-02-22 |  |  | Status update as of 2024-05-16. Remediation activities progressing. | 2024-05-16 | Henry Weber | 43629729 | N10112 | Electronic Trading | 3200, 2210, 4300 | UBS Financial Services Inc, UBS Europe SE Frankfurt, UBS Securities Japan Co Ltd | CTRL-8110054933 | ISSUE-3392080953 | Regulatory Compliance, Talent and Resource Management
ISSUE-5774080233 | Self-Identified Issue - Escalation Process Failure - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Intragroup Dependencies processes that require remediation. | Lack of automated controls and manual workarounds | Documentation gaps and missing evidence | Financial losses from operational errors | All Intragroup Dependencies controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2024-03-13 | 2024-08-25 | 1 | 0 | 1 | 3 | 2023-08-25 | 2025-05-01 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Matthew Jackson | 96203262 | Margaret Jackson | 15352233 | Robert White | 25216804 | Thomas Mueller | 82509424 | David Johnson | 79372824 | Fail | N/A | N/A | Fail | Fail | [8 empty] | TRUE | FALSE | TRUE | Operating Committee |  | 2024-06-20 | Manual Control, Key Control, SOX Control | 2023-08-25 | 2023-09-01 | 2023-11-05 | 2025-10-06 | 2024-08-06 | Status update as of 2025-05-01. Remediation activities progressing. | 2025-05-01 | Linda Miller | 37592422 | N40113, N10122, N14963 | Control Testing, Options Trading, Deal Execution | 4300 | UBS Securities Japan Co Ltd | CTRL-4163119785, CTRL-6241752544, CTRL-9703905715 |  | Intragroup Dependencies
ISSUE-2867302554 | Self-Identified - System Configuration Error - Global Wealth Management | Self-Identified | Management self-assessment identified weaknesses in Anti-Money Laundering processes that require remediation. | Resource constraints and competing priorities | Inconsistent application of procedures | Client complaints and relationship impact | All Anti-Money Laundering controls operating effectively with documented evidence and no exceptions. | Open-Grace Period | Red | Issue Mitigation Date at significant risk. Key dependencies delayed and remediation plan requires revision. | 2025-02-11 | 2025-02-11 | 0 | 1 | 5 | 5 | 2024-06-05 | 2025-11-20 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20200 | High Net Worth | N20210 | Wealth Planning | N20211 | Tax Advisory | N20212 | Estate Planning | N20213 | Trust Services | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | William Li | 77489633 | Benjamin Weber | 50446607 | David Young |  | Emma Wright | 30981381 | Kevin Moore | 28304809 | N/A | Fail | N/A | Fail | N/A | [8 empty] | TRUE | FALSE | FALSE | Risk Committee |  |  | Key Control | 2024-06-05 | 2024-06-06 | 2024-08-10 |  |  | Status update as of 2025-11-20. Remediation activities progressing. | 2025-11-20 | Edward Harris | 82095327 | N10122, N20213, N20113 | Options Trading, Trust Services, Investment Advisory | 4100, 2210, 3100 | UBS AG Hong Kong Branch, UBS Europe SE Frankfurt, UBS Securities LLC | CTRL-8934927891, CTRL-8429141456 |  | Anti-Money Laundering
ISSUE-4919706735 | Self-Identified Issue - Escalation Process Failure - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Business Continuity processes that require remediation. | Insufficient training and awareness among staff | Control exceptions not properly escalated | Increased scrutiny from regulators | All Business Continuity controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-10-24 | 2025-04-13 | 1 | 2 | 4 | 4 | 2024-04-09 | 2024-09-23 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Nancy Weber | 27969238 | Barbara Garcia | 63255602 |  |  | Evelyn Wilson | 79006257 | Lucas Young | 31370471 | Pass | N/A | N/A | N/A | Pass | [8 empty] | FALSE | FALSE | TRUE | Audit Committee |  |  | Financial Reporting Control, BCBS239 Control | 2024-04-09 | 2024-04-11 | 2024-06-20 |  |  | Status update as of 2024-09-23. Remediation activities progressing. | 2024-09-23 | Harper Kumar | 62088975 | N40213, N10112 | DevOps, Electronic Trading | 4100 | UBS AG Hong Kong Branch | CTRL-6317189421 | ISSUE-3694860228, ISSUE-2137651678 | Business Continuity
ISSUE-4274958945 | Self-Identified Issue - Process Execution Gap - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Regulatory Compliance processes that require remediation. | Inadequate process documentation and procedures | Inconsistent application of procedures | Increased scrutiny from regulators | All Regulatory Compliance controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2024-01-13 | 2024-05-30 | 1 | 2 | 4 | 4 | 2023-06-04 | 2025-08-01 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Karen Wright | 33987338 | Maria Wright | 44061458 | Brian Li | 63436070 | Lucas Davis | 40839382 | Matthew Wilson | 23459168 | Pass | N/A | Fail | Fail | N/A | [8 empty] | TRUE | TRUE | FALSE | Risk Committee | Business priority assessment completed. |  | Automated Control, IT General Control | 2023-06-04 | 2023-06-07 | 2023-07-08 |  |  | Status update as of 2025-08-01. Remediation activities progressing. | 2025-08-01 | Michael Moore | 59772648 | N40413 | Capital Calculations | 4200 | UBS AG Singapore Branch | CTRL-8086172302, CTRL-1945826486, CTRL-4274958945, CTRL-4131575764 | ISSUE-4466589567 | Regulatory Compliance, Market Conduct
ISSUE-9592390865 | Control Self-Assessment - Evidence Retention Issue - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Process Execution processes that require remediation. | Legacy systems limitations | Documentation gaps and missing evidence | Reputational damage to the firm | All Process Execution controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2023-02-24 | 2023-02-24 | 0 | 1 | 3 | 5 | 2022-03-10 | 2024-08-25 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SB | UK & Ireland | C782 | United Kingdom | 2100 | UBS AG London Branch | Henry Garcia | 47035619 | Patricia Li | 99880518 |  | 79490249 | James Jones | 22101856 | [15 empty] | FALSE | FALSE | FALSE | Operating Committee |  | 2025-04-10 | Automated Control, Key Control | 2022-03-10 | 2022-03-19 | 2022-04-20 |  |  | Status update as of 2024-08-25. Remediation activities progressing. | 2024-08-25 | Christopher Miller | 84978145 | N40313 | Transaction Monitoring | 4100, 2100 | UBS AG Hong Kong Branch, UBS AG London Branch | CTRL-6687206971, CTRL-5067116918, CTRL-6488854841 |  | Process Execution
ISSUE-6687206971 | Control Self-Assessment - Evidence Retention Issue - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Conduct Risk processes that require remediation. | Resource constraints and competing priorities | Inconsistent application of procedures | Increased scrutiny from regulators | All Conduct Risk controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2023-01-28 | 2023-01-28 | 0 | 1 | 2 | 4 | 2022-02-26 | 2024-03-10 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | John Smith | 45346197 | Evelyn Weber | 22483514 |  | 55901507 | William Anderson | 73962190 | Robert Li | 39335449 | N/A | Fail | Pass | N/A | N/A | [8 empty] | TRUE | FALSE | TRUE | Audit Committee |  |  | BCBS239 Control | 2022-02-26 | 2022-03-05 | 2022-05-20 |  |  | Status update as of 2024-03-10. Remediation activities progressing. | 2024-03-10 | Evelyn Li | 30937370 | N10122 | Options Trading | 4300 | UBS Securities Japan Co Ltd | CTRL-7114223633 | ISSUE-2867302554 | Conduct Risk
ISSUE-1083651970 | Self-Identified - System Configuration Error - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Operational Resilience processes that require remediation. | Inadequate process documentation and procedures | Control exceptions not properly escalated | Financial losses from operational errors | All Operational Resilience controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2024-10-14 | 2024-12-15 | 1 | 1 | 5 | 5 | 2024-03-25 | 2024-02-25 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40400 | Group Finance | N40410 | Financial Reporting | N40411 | Regulatory Reporting | N40412 | Capital Reporting | N40413 | Capital Calculations | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Amelia King | 26155543 | Jessica King | 52365995 | James Thomas |  | Benjamin Chen | 58533442 | Margaret Mueller | 35119175 | N/A | Fail | Pass | Fail | Fail | [8 empty] | FALSE | FALSE | TRUE | Executive Committee |  |  | Financial Reporting Control, IT General Control | 2024-03-25 | 2024-04-03 | 2024-05-22 |  |  | Status update as of 2024-02-25. Remediation activities progressing. | 2024-02-25 | Amelia Rodriguez | 87295013 | N20113, N10122, N20213 | Investment Advisory, Options Trading, Trust Services | 4200 | UBS AG Singapore Branch | CTRL-2625792787, CTRL-5693307665, CTRL-8763140509, CTRL-5710360983 |  | Operational Resilience, Anti-Money Laundering
ISSUE-2320763135 | Self-Assessment Finding - Documentation Deficiency - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Conduct Risk processes that require remediation. | Organizational changes affecting ownership | Documentation gaps and missing evidence | Financial losses from operational errors | All Conduct Risk controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2024-11-03 | 2025-03-05 | 1 | 1 | 2 | 3 | 2024-03-20 | 2025-08-24 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Evelyn Mueller | 20746107 | Harper Wilson | 63290556 |  |  | Andrew Brown | 13538638 | [15 empty] | FALSE | TRUE | TRUE | Operating Committee |  |  | Regulatory Control, BCBS239 Control | 2024-03-20 | 2024-03-28 | 2024-06-05 |  |  | Status update as of 2025-08-24. Remediation activities progressing. | 2025-08-24 | David Young | 94084814 | N14963 | Deal Execution | 1000, 2100, 4200 | UBS AG Zurich, UBS AG London Branch, UBS AG Singapore Branch | CTRL-4332894265, CTRL-5774080233, CTRL-8047877267 | ISSUE-9285415473, ISSUE-7567496105 | Conduct Risk
ISSUE-9957813353 | Self-Identified Issue - Escalation Process Failure - Global Wealth Management | Self-Identified | Management self-assessment identified weaknesses in Organizational Culture processes that require remediation. | Insufficient training and awareness among staff | Control exceptions not properly escalated | Increased scrutiny from regulators | All Organizational Culture controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2023-04-15 | 2023-04-15 | 0 | 1 | 2 | 3 | 2022-09-08 | 2024-11-01 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20200 | High Net Worth | N20210 | Wealth Planning | N20211 | Tax Advisory | N20212 | Estate Planning | N20213 | Trust Services | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Robert Smith | 32462726 | Sarah Davis | 63124490 | James Williams | 73789750 | Edward Martinez | 59848284 | Isabella Jackson | 31165928 | Fail | Pass | N/A | N/A | Fail | [8 empty] | TRUE | TRUE | FALSE | Audit Committee |  |  | Application Control | 2022-09-08 | 2022-09-16 | 2022-10-28 |  |  | Status update as of 2024-11-01. Remediation activities progressing. | 2024-11-01 | Karen Li | 68883853 | N20113, N10112, N40113 | Investment Advisory, Electronic Trading, Control Testing | 1000, 4300 | UBS AG Zurich, UBS Securities Japan Co Ltd | CTRL-2948728483 | ISSUE-1083651970, ISSUE-2948728483 | Organizational Culture
ISSUE-8086172302 | Management Identified - Control Operating Effectiveness - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Business Continuity processes that require remediation. | Inadequate process documentation and procedures | Increased error rates in processing | Client complaints and relationship impact | All Business Continuity controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2025-06-14 | 2025-06-14 | 0 | 2 | 2 | 3 | 2024-07-01 | 2025-03-18 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Sophia Harris | 45239935 | Isabella Harris | 77353558 |  | 28102047 | Andrew Taylor | 75479608 | Patricia Taylor | 85318641 | N/A | N/A | N/A | Pass | Pass | [8 empty] | TRUE | FALSE | FALSE | Operating Committee |  |  | IT General Control | 2024-07-01 | 2024-07-15 | 2024-08-23 |  |  | Status update as of 2025-03-18. Remediation activities progressing. | 2025-03-18 | John Taylor | 53048774 | N40413, N10112 | Capital Calculations, Electronic Trading | 1000, 4300 | UBS AG Zurich, UBS Securities Japan Co Ltd | CTRL-7517938612, CTRL-5693307665, CTRL-7567496105, CTRL-9963334018 | ISSUE-2625792787 | Business Continuity, Transaction Processing
ISSUE-1519709079 | Self-Identified Issue - Escalation Process Failure - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Regulatory Change processes that require remediation. | Inadequate process documentation and procedures | Increased error rates in processing | Financial losses from operational errors | All Regulatory Change controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2024-09-18 | 2024-09-18 | 0 | 0 | 5 | 4 | 2023-12-22 | 2024-08-29 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3200 | UBS Financial Services Inc | Michael White | 13954845 | Karen Schmidt | 40277197 |  | 98171888 | Lucas Garcia | 61298971 | Jessica Moore | 66013532 | Pass | N/A | Pass | Fail | Fail | [8 empty] | FALSE | FALSE | TRUE | Audit Committee |  |  | BCBS239 Control, CCAR Control, Regulatory Control | 2023-12-22 | 2024-01-14 | 2024-03-06 | 2025-06-20 | 2024-05-18 | Status update as of 2024-08-29. Remediation activities progressing. | 2024-08-29 | Linda Martinez | 98077934 | N14963, N30113, N10122 | Deal Execution, Portfolio Management, Options Trading | 2210, 4300, 1000 | UBS Europe SE Frankfurt, UBS Securities Japan Co Ltd, UBS AG Zurich | CTRL-8664882079, CTRL-1958682846 | ISSUE-1470939445, ISSUE-6924716023 | Regulatory Change, Client Suitability
ISSUE-1965067727 | Management Identified - Control Operating Effectiveness - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Third Party Management processes that require remediation. | Insufficient training and awareness among staff | Control exceptions not properly escalated | Increased scrutiny from regulators | All Third Party Management controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-01-25 | 2024-01-25 | 0 | 0 | 3 | 5 | 2023-07-01 | 2024-08-24 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N14952 | Investment Banking | N14960 | Advisory | N14961 | M&A | N14962 | Cross Border M&A | N14963 | Deal Execution | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Lucas Wright | 97183615 | Maria Anderson | 62004039 |  |  | Alexander Moore | 14325777 | Christopher Smith | 46219821 | Fail | Pass | N/A | N/A | Pass | [8 empty] | TRUE | TRUE | TRUE | Executive Committee | Business priority assessment completed. |  | Application Control, BCBS239 Control | 2023-07-01 | 2023-07-15 | 2023-08-25 | 2024-02-12 |  | Status update as of 2024-08-24. Remediation activities progressing. | 2024-08-24 | Edward White | 51996390 | N40413, N40313 | Capital Calculations, Transaction Monitoring | 2100, 3200, 4300 | UBS AG London Branch, UBS Financial Services Inc, UBS Securities Japan Co Ltd | CTRL-4095476665, CTRL-9963334018, CTRL-5728765136, CTRL-4274958945 |  | Third Party Management
ISSUE-1945826486 | Management Review Finding - Training Gap - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Technology Production Stability processes that require remediation. | Lack of automated controls and manual workarounds | Increased error rates in processing | Client complaints and relationship impact | All Technology Production Stability controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2025-09-26 | 2025-09-26 | 0 | 2 | 2 | 4 | 2024-10-16 | 2024-01-06 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Isabella Smith | 42844845 | Karen Schmidt | 93183589 | Harper Brown |  | Sophia Li | 14928616 | Charlotte Williams | 99522760 | N/A | N/A | Fail | Fail | Pass | [8 empty] | TRUE | TRUE | FALSE | Audit Committee |  |  | Automated Control, Manual Control, CCAR Control | 2024-10-16 | 2024-10-31 | 2025-01-01 |  |  | Status update as of 2024-01-06. Remediation activities progressing. | 2024-01-06 | Nancy Kumar | 14810369 | N20213 | Trust Services | 4100, 3100 | UBS AG Hong Kong Branch, UBS Securities LLC | CTRL-7114223633 |  | Technology Production Stability
ISSUE-3710566582 | Self-Assessment Finding - Documentation Deficiency - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Intragroup Dependencies processes that require remediation. | Lack of automated controls and manual workarounds | Inconsistent application of procedures | Client complaints and relationship impact | All Intragroup Dependencies controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2022-08-20 | 2022-08-20 | 0 | 2 | 3 | 4 | 2022-03-14 | 2025-10-04 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SB | UK & Ireland | C782 | United Kingdom | 2100 | UBS AG London Branch | Sophia Fischer | 85825317 | Robert Johnson | 37952515 | Elizabeth Li |  | Charlotte Schmidt | 14183991 | Elizabeth White | 94088862 | N/A | Pass | N/A | N/A | Fail | [8 empty] | TRUE | TRUE | FALSE | Operating Committee |  |  | Application Control | 2022-03-14 | 2022-04-12 | 2022-04-28 |  |  | Status update as of 2025-10-04. Remediation activities progressing. | 2025-10-04 | Maria Young | 50618137 | N40313 | Transaction Monitoring | 1000, 2100 | UBS AG Zurich, UBS AG London Branch | CTRL-4163119785, CTRL-1422701550, CTRL-2625792787 | ISSUE-3615507143, ISSUE-1958682846 | Intragroup Dependencies
ISSUE-6317189421 | Management Review Finding - Training Gap - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Conduct Risk processes that require remediation. | Insufficient training and awareness among staff | Inconsistent application of procedures | Client complaints and relationship impact | All Conduct Risk controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2025-10-11 | 2025-10-11 | 0 | 2 | 3 | 3 | 2024-11-15 | 2024-12-05 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3200 | UBS Financial Services Inc | Edward Fischer | 85659375 | Michael Brown | 94463223 |  |  | Sophia Weber | 93794410 | [15 empty] | TRUE | FALSE | FALSE | Risk Committee |  |  | Regulatory Control, CCAR Control | 2024-11-15 | 2024-12-05 | 2025-01-01 |  |  | Status update as of 2024-12-05. Remediation activities progressing. | 2024-12-05 | Sarah Mueller | 11906295 | N10122, N14963, N40313 | Options Trading, Deal Execution, Transaction Monitoring | 4300, 1000, 2210 | UBS Securities Japan Co Ltd, UBS AG Zurich, UBS Europe SE Frankfurt | CTRL-9894264595, CTRL-9786748825, CTRL-2948728483 |  | Conduct Risk
ISSUE-8664882079 | Self-Identified - System Configuration Error - Global Wealth Management | Self-Identified | Management self-assessment identified weaknesses in Organizational Culture processes that require remediation. | Insufficient training and awareness among staff | Delayed or incomplete reporting | Increased scrutiny from regulators | All Organizational Culture controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2024-12-20 | 2024-12-20 | 0 | 0 | 3 | 3 | 2024-06-02 | 2024-04-18 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20100 | Ultra High Net Worth | N20110 | Private Banking | N20111 | Client Advisory | N20112 | Portfolio Management | N20113 | Investment Advisory | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | William Mueller | 69845276 | Emma Lopez | 29978882 | James Williams | 45760499 | Charlotte Wang | 62523472 | [15 empty] | TRUE | FALSE | FALSE | Executive Committee |  |  | Manual Control | 2024-06-02 | 2024-06-10 | 2024-07-02 | 2025-01-28 | 2025-12-06 | Status update as of 2024-04-18. Remediation activities progressing. | 2024-04-18 | Andrew Davis | 86134185 | N30113, N40413, N20213 | Portfolio Management, Capital Calculations, Trust Services | 2100, 4100 | UBS AG London Branch, UBS AG Hong Kong Branch | CTRL-2970753705 |  | Organizational Culture
ISSUE-4700855390 | Management Identified - Control Operating Effectiveness - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Sanctions Compliance processes that require remediation. | Lack of automated controls and manual workarounds | Delayed or incomplete reporting | Financial losses from operational errors | All Sanctions Compliance controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-03-12 | 2024-03-12 | 0 | 0 | 1 | 4 | 2023-04-10 | 2024-10-22 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Henry Wilson | 81848989 | David Anderson | 33536332 | Charlotte Wilson |  | Oliver Chen | 87111463 | [15 empty] | TRUE | FALSE | FALSE | Operating Committee |  |  | Financial Reporting Control | 2023-04-10 | 2023-04-22 | 2023-05-19 | 2025-01-16 |  | Status update as of 2024-10-22. Remediation activities progressing. | 2024-10-22 | Matthew Wilson | 81624345 | N10122, N10112 | Options Trading, Electronic Trading | 4300, 4200 | UBS Securities Japan Co Ltd, UBS AG Singapore Branch | CTRL-4095476665, CTRL-8235363119 |  | Sanctions Compliance, Operational Resilience
ISSUE-2067970820 | Control Self-Assessment - Evidence Retention Issue - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Regulatory Change processes that require remediation. | Legacy systems limitations | Delayed or incomplete reporting | Increased scrutiny from regulators | All Regulatory Change controls operating effectively with documented evidence and no exceptions. | Closed | Green | Remediation on track. All action plans progressing as planned. | 2025-03-14 | 2025-03-14 | 0 | 0 | 2 | 5 | 2024-06-24 | 2025-05-05 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40300 | Group Compliance | N40310 | Regulatory Compliance | N40311 | Financial Crime | N40312 | AML Operations | N40313 | Transaction Monitoring | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Jennifer Johnson | 63905855 | Margaret Moore | 69857441 |  |  | Edward Taylor | 88306842 | Jessica Moore | 47302753 | Pass | Pass | Pass | N/A | Fail | [8 empty] | TRUE | FALSE | TRUE | Executive Committee |  |  | Financial Reporting Control | 2024-06-24 | 2024-07-07 | 2024-08-02 | 2025-03-13 | 2025-01-13 | Status update as of 2025-05-05. Remediation activities progressing. | 2025-05-05 | Thomas Kumar | 11636220 | N30113, N40413 | Portfolio Management, Capital Calculations | 4300, 4200 | UBS Securities Japan Co Ltd, UBS AG Singapore Branch | CTRL-8995970241 | ISSUE-8763140509, ISSUE-3694860228 | Regulatory Change, Sanctions Compliance
ISSUE-3363629219 | Management Identified - Control Operating Effectiveness - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Sanctions Compliance processes that require remediation. | Insufficient training and awareness among staff | Inconsistent application of procedures | Financial losses from operational errors | All Sanctions Compliance controls operating effectively with documented evidence and no exceptions. | Open-Grace Period | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2023-04-09 | 2023-09-11 | 1 | 1 | 1 | 3 | 2023-01-03 | 2025-11-19 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3100 | UBS Securities LLC | Nancy Miller | 32645646 | William Kumar | 36720922 |  | 64262755 | Mia Moore | 67002833 | Susan Schmidt | 88103795 | N/A | Fail | N/A | Fail | Fail | [8 empty] | FALSE | FALSE | FALSE | Operating Committee |  |  | Regulatory Control | 2023-01-03 | 2023-01-19 | 2023-03-05 |  |  | Status update as of 2025-11-19. Remediation activities progressing. | 2025-11-19 | Daniel Rodriguez | 13989423 | N10112 | Electronic Trading | 4300 | UBS Securities Japan Co Ltd | CTRL-4466589567 |  | Sanctions Compliance, Regulatory Compliance
ISSUE-5161807235 | Self-Assessment Finding - Documentation Deficiency - Global Wealth Management | Self-Identified | Management self-assessment identified weaknesses in Operational Resilience processes that require remediation. | Lack of automated controls and manual workarounds | Increased error rates in processing | Increased scrutiny from regulators | All Operational Resilience controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2025-11-21 | 2025-11-21 | 0 | 1 | 3 | 4 | 2024-12-23 | 2024-12-21 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20100 | Ultra High Net Worth | N20110 | Private Banking | N20111 | Client Advisory | N20112 | Portfolio Management | N20113 | Investment Advisory | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Robert Taylor | 65608317 | Patricia Mueller | 93881231 | Karen Anderson | 94267786 | Jessica Anderson | 87422596 | Susan Thomas | 98691908 | N/A | Fail | Fail | N/A | N/A | [8 empty] | FALSE | TRUE | TRUE | Operating Committee |  |  | Regulatory Control, IT General Control, Manual Control | 2024-12-23 | 2025-01-03 | 2025-03-18 | 2024-03-06 |  | Status update as of 2024-12-21. Remediation activities progressing. | 2024-12-21 | Harper Martin | 45827376 | N14963, N20213 | Deal Execution, Trust Services | 3100, 4300, 2210 | UBS Securities LLC, UBS Securities Japan Co Ltd, UBS Europe SE Frankfurt | CTRL-5710360983 |  | Operational Resilience
ISSUE-6009268066 | Self-Identified - System Configuration Error - Asset Management | Self-Identified | Management self-assessment identified weaknesses in Physical Security processes that require remediation. | Organizational changes affecting ownership | Delayed or incomplete reporting | Financial losses from operational errors | All Physical Security controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2023-07-26 | 2023-07-26 | 0 | 0 | 1 | 5 | 2022-10-24 | 2025-01-11 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Sophia Jackson | 43954789 | Karen White | 51509315 | Maria Davis | 41726640 | Matthew White | 11055770 | Patricia Mueller | 50384524 | Pass | Pass | Fail | Pass | Pass | [8 empty] | FALSE | FALSE | FALSE | Risk Committee |  |  | Application Control, IT General Control | 2022-10-24 | 2022-11-23 | 2023-01-15 | 2024-12-06 |  | Status update as of 2025-01-11. Remediation activities progressing. | 2025-01-11 | Linda Miller | 31520919 | N20213, N40313, N10122 | Trust Services, Transaction Monitoring, Options Trading | 4200, 3200 | UBS AG Singapore Branch, UBS Financial Services Inc | CTRL-4095476665, CTRL-8987073217, CTRL-1958682846 | ISSUE-1519709079 | Physical Security, Regulatory Compliance
ISSUE-7249213370 | Self-Identified Issue - Escalation Process Failure - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Regulatory Compliance processes that require remediation. | Resource constraints and competing priorities | Increased error rates in processing | Potential regulatory sanctions or fines | All Regulatory Compliance controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2025-08-08 | 2025-11-03 | 1 | 1 | 2 | 5 | 2024-11-17 | 2025-10-25 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Jessica Garcia | 49017499 | Barbara Thompson | 20627779 | Andrew Fischer |  | Lucas Fischer | 43373708 | Jessica Thompson | 49658873 | N/A | Pass | N/A | Pass | Pass | [8 empty] | TRUE | FALSE | FALSE | Risk Committee |  |  | Financial Reporting Control, Regulatory Control | 2024-11-17 | 2024-12-06 | 2024-12-22 | 2025-05-30 |  | Status update as of 2025-10-25. Remediation activities progressing. | 2025-10-25 | Emma Davis | 98795539 | N14963, N40413 | Deal Execution, Capital Calculations | 2100, 4300 | UBS AG London Branch, UBS Securities Japan Co Ltd | CTRL-6317189421, CTRL-6924716023, CTRL-8235363119, CTRL-4289233844 | ISSUE-7517938612, ISSUE-2811967841 | Regulatory Compliance
ISSUE-3328710672 | Self-Assessment Finding - Documentation Deficiency - Global Wealth Management | Self-Identified | Management self-assessment identified weaknesses in Physical Security processes that require remediation. | Resource constraints and competing priorities | Delayed or incomplete reporting | Increased scrutiny from regulators | All Physical Security controls operating effectively with documented evidence and no exceptions. | Open | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2024-02-20 | 2024-02-20 | 0 | 1 | 2 | 3 | 2023-08-05 | 2025-07-19 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20200 | High Net Worth | N20210 | Wealth Planning | N20211 | Tax Advisory | N20212 | Estate Planning | N20213 | Trust Services | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Kevin Mueller | 42392076 | Jennifer Thompson | 77816807 |  |  | Maria Mueller | 94153110 | Joshua Li | 26617902 | Pass | N/A | Pass | Fail | Fail | [8 empty] | TRUE | FALSE | FALSE | Audit Committee | Business priority assessment completed. | 2025-08-02 | Manual Control, BCBS239 Control, Financial Reporting Control | 2023-08-05 | 2023-08-15 | 2023-09-22 |  |  | Status update as of 2025-07-19. Remediation activities progressing. | 2025-07-19 | Brian Rodriguez | 60689435 | N20113, N10122, N30113 | Investment Advisory, Options Trading, Portfolio Management | 3100, 4200, 1000 | UBS Securities LLC, UBS AG Singapore Branch, UBS AG Zurich | CTRL-7825844140, CTRL-5693307665, CTRL-8168204967, CTRL-5567816720 | ISSUE-6241752544 | Physical Security
ISSUE-8507497883 | Self-Identified Issue - Process Execution Gap - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Intragroup Dependencies processes that require remediation. | Lack of automated controls and manual workarounds | Control exceptions not properly escalated | Client complaints and relationship impact | All Intragroup Dependencies controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2025-09-16 | 2026-03-14 | 1 | 4 | 4 | 3 | 2024-11-28 | 2025-05-25 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40100 | Group Risk Control | N40110 | Non-Financial Risk | N40111 | Operational Risk | N40112 | Risk Assessment | N40113 | Control Testing | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Lucas Lopez | 71433172 | Lucas Davis | 38540398 |  |  | Henry Kumar | 25940510 | [15 empty] | FALSE | TRUE | TRUE | Operating Committee |  |  | SOX Control | 2024-11-28 | 2024-12-10 | 2025-01-16 |  |  | Status update as of 2025-05-25. Remediation activities progressing. | 2025-05-25 | Maria Fischer | 49457501 | N10112, N14963 | Electronic Trading, Deal Execution | 4200 | UBS AG Singapore Branch | CTRL-3392080953 | ISSUE-8429141456 | Intragroup Dependencies, Legal Risk
ISSUE-1245522987 | Self-Identified - System Configuration Error - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Data Management processes that require remediation. | Resource constraints and competing priorities | Control exceptions not properly escalated | Financial losses from operational errors | All Data Management controls operating effectively with documented evidence and no exceptions. | Open-Grace Period | Red | Issue Mitigation Date at significant risk. Key dependencies delayed and remediation plan requires revision. | 2025-04-03 | 2025-09-01 | 1 | 4 | 4 | 5 | 2024-07-15 | 2025-09-12 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10110 | Cash Equities | N10111 | Execution Services | N10112 | Electronic Trading | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SGE | Germany & Austria | C276 | Germany | 2210 | UBS Europe SE Frankfurt | Robert Garcia | 93855267 | Margaret Martin | 61973818 |  |  | Kevin Williams | 99985448 | Matthew Schmidt | 96693449 | Pass | Pass | N/A | Pass | N/A | [8 empty] | FALSE | TRUE | TRUE | Audit Committee | Business priority assessment completed. |  | Automated Control | 2024-07-15 | 2024-08-01 | 2024-08-26 |  |  | Status update as of 2025-09-12. Remediation activities progressing. | 2025-09-12 | Andrew Johnson | 26144134 | N40313, N14963, N10112 | Transaction Monitoring, Deal Execution, Electronic Trading | 3100, 2210 | UBS Securities LLC, UBS Europe SE Frankfurt | CTRL-7635473142, CTRL-6687206971, CTRL-6633778586, CTRL-4332894265 |  | Data Management, Cyber and Information Security
ISSUE-1676168421 | Control Self-Assessment - Evidence Retention Issue - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Financial Crime Prevention processes that require remediation. | Legacy systems limitations | Delayed or incomplete reporting | Financial losses from operational errors | All Financial Crime Prevention controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2025-02-25 | 2025-02-25 | 0 | 2 | 2 | 5 | 2024-04-13 | 2025-10-13 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10110 | Cash Equities | N10111 | Execution Services | N10112 | Electronic Trading | N0000 | UBS Group AG (Regional) | AMER | Americas | SNA | North America | C840 | United States | 3200 | UBS Financial Services Inc | Evelyn Thompson | 84511273 | Matthew Williams | 10134359 | Margaret Weber | 32465588 | James Brown | 74717944 | Sarah Mueller | 61023340 | Fail | N/A | Pass | N/A | N/A | [8 empty] | FALSE | TRUE | TRUE | Risk Committee |  |  | CCAR Control | 2024-04-13 | 2024-05-07 | 2024-06-17 |  |  | Status update as of 2025-10-13. Remediation activities progressing. | 2025-10-13 | Sarah Thompson | 38299831 | N40313, N30113, N40413 | Transaction Monitoring, Portfolio Management, Capital Calculations | 3200, 4200, 4100 | UBS Financial Services Inc, UBS AG Singapore Branch, UBS AG Hong Kong Branch | CTRL-6884882440, CTRL-5728765136, CTRL-9894847574, CTRL-4332894265 |  | Financial Crime Prevention
ISSUE-1798112150 | Management Identified - Control Operating Effectiveness - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Transaction Processing processes that require remediation. | Organizational changes affecting ownership | Increased error rates in processing | Increased scrutiny from regulators | All Transaction Processing controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-12-03 | 2025-02-15 | 1 | 4 | 4 | 5 | 2024-09-02 | 2025-02-27 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | William Johnson | 69750614 | Mia Li | 60516391 | John White |  | James Davis | 72101540 | [15 empty] | FALSE | TRUE | FALSE | Risk Committee |  |  | Financial Reporting Control, BCBS239 Control | 2024-09-02 | 2024-09-05 | 2024-11-23 |  |  | Status update as of 2025-02-27. Remediation activities progressing. | 2025-02-27 | Margaret Fischer | 39681939 | N40213 | DevOps | 2100, 1000 | UBS AG London Branch, UBS AG Zurich | CTRL-6317189421, CTRL-6633778586, CTRL-7665963761, CTRL-3746317213 |  | Transaction Processing
ISSUE-3660223333 | Self-Assessment Finding - Documentation Deficiency - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Data Management processes that require remediation. | Insufficient training and awareness among staff | Control exceptions not properly escalated | Potential regulatory sanctions or fines | All Data Management controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2023-06-14 | 2023-06-14 | 0 | 1 | 1 | 3 | 2022-10-19 | 2025-10-08 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10110 | Cash Equities | N10111 | Execution Services | N10112 | Electronic Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Amelia Moore | 45164890 | Amelia Wang | 84424395 |  |  | Amelia Mueller | 23581521 | [15 empty] | TRUE | TRUE | FALSE | Risk Committee |  |  | BCBS239 Control, Financial Reporting Control | 2022-10-19 | 2022-11-14 | 2022-12-11 |  |  | Status update as of 2025-10-08. Remediation activities progressing. | 2025-10-08 | Henry Thompson | 18774822 | N14963 | Deal Execution | 3100 | UBS Securities LLC | CTRL-6687206971, CTRL-7805745017 |  | Data Management
ISSUE-8370987661 | Self-Identified - System Configuration Error - Global Wealth Management | Self-Identified | Management self-assessment identified weaknesses in Intragroup Dependencies processes that require remediation. | Legacy systems limitations | Increased error rates in processing | Financial losses from operational errors | All Intragroup Dependencies controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2023-03-16 | 2023-03-16 | 0 | 2 | 3 | 3 | 2022-10-12 | 2024-01-10 00:00:00 | N00000 | All Functions | N20000 | Global Wealth Management | N20100 | Ultra High Net Worth | N20110 | Private Banking | N20111 | Client Advisory | N20112 | Portfolio Management | N20113 | Investment Advisory | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Patricia Fischer | 53765651 | Nancy Johnson | 86178952 | Lucas Martinez | 54325475 | Brian Harris | 61179711 | Harper Harris | 18550910 | N/A | Fail | Pass | Fail | Pass | [8 empty] | FALSE | FALSE | FALSE | Risk Committee |  |  | Key Control | 2022-10-12 | 2022-11-08 | 2022-12-25 |  |  | Status update as of 2024-01-10. Remediation activities progressing. | 2024-01-10 | Edward Lopez | 13602203 | N20113 | Investment Advisory | 4200 | UBS AG Singapore Branch | CTRL-7665963761, CTRL-4026113008, CTRL-5996775663 |  | Intragroup Dependencies, Legal Risk
ISSUE-6320115677 | Management Review Finding - Training Gap - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Market Conduct processes that require remediation. | Insufficient training and awareness among staff | Delayed or incomplete reporting | Financial losses from operational errors | All Market Conduct controls operating effectively with documented evidence and no exceptions. | Open-Grace Period | Amber | Issue Mitigation Date at risk. Mitigation activities behind schedule but recovery plan in place. | 2025-02-05 | 2025-02-05 | 0 | 1 | 1 | 3 | 2024-04-21 | 2024-04-23 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Harper Fischer | 68008992 | Andrew Wilson | 91028510 | Jennifer Taylor | 71600090 | Sarah Taylor | 10999023 | [15 empty] | TRUE | FALSE | TRUE | Executive Committee |  |  | Automated Control, Application Control | 2024-04-21 | 2024-05-06 | 2024-06-19 |  |  | Status update as of 2024-04-23. Remediation activities progressing. | 2024-04-23 | Brian Williams | 22227594 | N40213, N30113 | DevOps, Portfolio Management | 3200, 3100, 4300 | UBS Financial Services Inc, UBS Securities LLC, UBS Securities Japan Co Ltd | CTRL-3694860228, CTRL-5728765136 |  | Market Conduct
ISSUE-1311570307 | Self-Identified - System Configuration Error - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Outsourcing Risk processes that require remediation. | Organizational changes affecting ownership | Documentation gaps and missing evidence | Potential regulatory sanctions or fines | All Outsourcing Risk controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-09-22 | 2024-09-22 | 0 | 1 | 3 | 3 | 2024-03-08 | 2024-03-08 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Harper Martin | 50471241 | Edward Lopez | 23665188 | Brian Wilson |  | Benjamin Chen | 94674464 | [15 empty] | FALSE | TRUE | FALSE | Audit Committee |  |  | Application Control, SOX Control | 2024-03-08 | 2024-03-19 | 2024-04-08 | 2025-09-15 |  | Status update as of 2024-03-08. Remediation activities progressing. | 2024-03-08 | Nancy Young | 61321020 | N20113, N40313, N10112 | Investment Advisory, Transaction Monitoring, Electronic Trading | 2100 | UBS AG London Branch | CTRL-3392080953 |  | Outsourcing Risk, Technology Production Stability
ISSUE-2139027119 | Self-Identified - System Configuration Error - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Organizational Culture processes that require remediation. | Resource constraints and competing priorities | Delayed or incomplete reporting | Reputational damage to the firm | All Organizational Culture controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2024-12-21 | 2025-04-22 | 1 | 0 | 1 | 4 | 2024-09-05 | 2025-10-08 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Charlotte Mueller | 43207452 | Edward Wilson | 11655896 |  |  | Thomas Harris | 88673120 | Isabella Taylor | 66766698 | Pass | Fail | Fail | N/A | Fail | [8 empty] | FALSE | FALSE | FALSE | Risk Committee |  |  | CCAR Control, Regulatory Control | 2024-09-05 | 2024-09-29 | 2024-10-18 | 2025-02-11 |  | Status update as of 2025-10-08. Remediation activities progressing. | 2025-10-08 | Jennifer Smith | 32602089 | N10112, N10122 | Electronic Trading, Options Trading | 4200 | UBS AG Singapore Branch | CTRL-1945826486, CTRL-4131575764, CTRL-8664882079, CTRL-9573276057 |  | Organizational Culture
ISSUE-9303285822 | Self-Identified - System Configuration Error - Asset Management | Self-Identified | Management self-assessment identified weaknesses in Intragroup Dependencies processes that require remediation. | Inadequate process documentation and procedures | Control exceptions not properly escalated | Potential regulatory sanctions or fines | All Intragroup Dependencies controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2025-01-25 | 2025-01-25 | 0 | 1 | 2 | 4 | 2024-07-11 | 2024-03-01 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | EMEA | Europe Middle East Africa | SCH | Switzerland | C756 | Switzerland | 1000 | UBS AG Zurich | Margaret Miller | 95420677 | Henry Garcia | 49342650 |  |  | William Wang | 13981790 | Nancy Jackson | 74142265 | Fail | N/A | Pass | Pass | Pass | [8 empty] | FALSE | TRUE | TRUE | Risk Committee |  |  | Automated Control, Manual Control | 2024-07-11 | 2024-08-05 | 2024-08-27 | 2025-05-12 |  | Status update as of 2024-03-01. Remediation activities progressing. | 2024-03-01 | Andrew Wang | 91117376 | N30113, N40413 | Portfolio Management, Capital Calculations | 4100, 1000, 2210 | UBS AG Hong Kong Branch, UBS AG Zurich, UBS Europe SE Frankfurt | CTRL-3710566582, CTRL-7483366056, CTRL-7805745017 |  | Intragroup Dependencies
ISSUE-4783282817 | Self-Identified - System Configuration Error - Asset Management | Self-Identified | Management self-assessment identified weaknesses in Technology Production Stability processes that require remediation. | Organizational changes affecting ownership | Inconsistent application of procedures | Reputational damage to the firm | All Technology Production Stability controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2022-07-24 | 2022-11-02 | 1 | 1 | 2 | 4 | 2022-02-22 | 2025-12-17 00:00:00 | N00000 | All Functions | N30000 | Asset Management | N30100 | Traditional Investments | N30110 | Fixed Income | N30111 | Credit | N30112 | Investment Grade | N30113 | Portfolio Management | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Andrew Martin | 98614357 | Alexander Smith | 95640742 | Robert Johnson | 16141035 | Robert Young | 41347711 | Edward Lopez | 63709262 | N/A | N/A | Pass | Fail | Fail | [8 empty] | FALSE | TRUE | FALSE | Operating Committee |  |  | Automated Control, Manual Control, Key Control | 2022-02-22 | 2022-02-27 | 2022-04-24 | 2024-03-30 |  | Status update as of 2025-12-17. Remediation activities progressing. | 2025-12-17 | Jennifer King | 32555671 | N10122, N40213 | Options Trading, DevOps | 3100, 2210, 4200 | UBS Securities LLC, UBS Europe SE Frankfurt, UBS AG Singapore Branch | CTRL-7146318035, CTRL-9894847574 |  | Technology Production Stability
ISSUE-4776436931 | Self-Assessment Finding - Documentation Deficiency - Investment Bank | Self-Identified | Management self-assessment identified weaknesses in Outsourcing Risk processes that require remediation. | Resource constraints and competing priorities | Documentation gaps and missing evidence | Reputational damage to the firm | All Outsourcing Risk controls operating effectively with documented evidence and no exceptions. | Open-Grace Period | Green | Remediation on track. All action plans progressing as planned. | 2024-05-10 | 2024-07-10 | 1 | 1 | 4 | 5 | 2023-06-12 | 2025-11-12 00:00:00 | N00000 | All Functions | N10000 | Investment Bank | N10007 | Global Markets | N10100 | Equities | N10120 | Derivatives | N10121 | Flow Derivatives | N10122 | Options Trading | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C702 | Singapore | 4200 | UBS AG Singapore Branch | Daniel Jones | 96434410 | Elizabeth White | 61224263 | Karen Thompson | 40004485 | Michael Davis | 49054205 | Isabella Davis | 21964091 | Fail | N/A | N/A | Pass | N/A | [8 empty] | TRUE | FALSE | TRUE | Operating Committee | Business priority assessment completed. |  | Regulatory Control | 2023-06-12 | 2023-06-14 | 2023-08-18 |  |  | Status update as of 2025-11-12. Remediation activities progressing. | 2025-11-12 | Kevin Taylor | 62096010 | N30113, N40413 | Portfolio Management, Capital Calculations | 1000, 3200, 4100 | UBS AG Zurich, UBS Financial Services Inc, UBS AG Hong Kong Branch | CTRL-4460967357, CTRL-5284391408 |  | Outsourcing Risk
ISSUE-6882074066 | Control Self-Assessment - Evidence Retention Issue - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Sanctions Compliance processes that require remediation. | Inadequate process documentation and procedures | Inconsistent application of procedures | Client complaints and relationship impact | All Sanctions Compliance controls operating effectively with documented evidence and no exceptions. | Completed | Green | Remediation on track. All action plans progressing as planned. | 2023-06-21 | 2023-06-21 | 0 | 1 | 1 | 4 | 2022-10-29 | 2025-11-12 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C344 | Hong Kong | 4100 | UBS AG Hong Kong Branch | Mia Schmidt | 87037211 | Andrew Thomas | 76441201 |  | 17893691 | Elizabeth Martinez | 38268009 | Daniel Brown | 34027688 | Fail | N/A | Fail | Fail | N/A | [8 empty] | TRUE | TRUE | FALSE | Operating Committee |  |  | IT General Control, Automated Control | 2022-10-29 | 2022-11-01 | 2022-12-31 | 2024-10-16 |  | Status update as of 2025-11-12. Remediation activities progressing. | 2025-11-12 | David Taylor | 83552661 | N10122, N14963 | Options Trading, Deal Execution | 2100, 4200 | UBS AG London Branch, UBS AG Singapore Branch | CTRL-4095476665, CTRL-1945826486, CTRL-8934927891 |  | Sanctions Compliance
ISSUE-5972484792 | Management Identified - Control Operating Effectiveness - Group Functions | Self-Identified | Management self-assessment identified weaknesses in Third Party Management processes that require remediation. | Organizational changes affecting ownership | Delayed or incomplete reporting | Potential regulatory sanctions or fines | All Third Party Management controls operating effectively with documented evidence and no exceptions. | Open | Green | Remediation on track. All action plans progressing as planned. | 2024-06-02 | 2024-06-02 | 0 | 1 | 2 | 3 | 2024-01-12 | 2024-05-31 00:00:00 | N00000 | All Functions | N40000 | Group Functions | N40200 | Group Technology | N40210 | Infrastructure | N40211 | Cloud Services | N40212 | Platform Engineering | N40213 | DevOps | N0000 | UBS Group AG (Regional) | APAC | Asia Pacific | SAP | Asia Pacific | C392 | Japan | 4300 | UBS Securities Japan Co Ltd | Andrew Anderson | 17042688 | Mia Wang | 89643778 |  |  | Patricia Jackson | 14562440 | Mia Jackson | 63236763 | Fail | Fail | N/A | N/A | Pass | [8 empty] | FALSE | TRUE | FALSE | Executive Committee |  |  | Key Control, SOX Control | 2024-01-12 | 2024-01-16 | 2024-02-16 |  |  | Status update as of 2024-05-31. Remediation activities progressing. | 2024-05-31 | Mia Lopez | 96088502 | N40313, N20113, N10112 | Transaction Monitoring, Investment Advisory, Electronic Trading | 4300, 1000, 4100 | UBS Securities Japan Co Ltd, UBS AG Zurich, UBS AG Hong Kong Branch | CTRL-4289233844 |  | Third Party Management, Intragroup Dependencies